TRANSMISSION CORPORATION OF ANDHRA PRADESH LIMITED

| # From : | To : |  |
| --- | --- | --- |
| The Chief Engineer, | M/s. Larsen & Toubro Limited, |  |
| Construction 400KV, | Power Transmission & Distribution |  |
| APTRANSCO,Vidyut soudha, | Mount Poonamallee Road, Manapakkam, |  |
| Hyderabad – 5000 082. | P.B.No. 979, Chennai – 600089, India, |  |
| Fax. No. 0 40 – 23323565. | Ph:- +91-44-22704000, 22705000 |  |

P.O.No. 15/OC.583 /CE/400kV/SEPMI/D2-A3/VEL-YMG/L&T/D.No. 247/2013, Dt. 13.12.2013

Sir(s),

Sub:	Design, Engineering, Civil & Construction works, Erection, Testing and Commissioning for execution of  400kV QMDC Line  from existing 400kV SS Veltoor to YEMMIGANOOR(Common point) of a length of  95.24 kM (Approx.) - Detailed Erection Purchase Order – Issued – Reg.

Ref:   1.   Bid no. e-EHVT-10/2013.

- Your offer against Bid no. e-EHVT-10/2013.

- Your Lr No.LTC/PTD/APTRANSCO/2013-14/21/PRN/2184/A dt: 21-10-2013.

4. L.O.I. No.CE/400KV/SE/PM-I /D1A3/e-EHVT-10/2013/L&T/D.No.222  /2013, Dt.  11.11.2013

5. Your Lr.No. LTC/PTD/APTRANSCO/2013-14/21/PRN/2290, dt: 16-11-2013.

(acceptance of LOI).

-oOo-

I, acting for and on behalf of and by the order and direction of the TRANSMISSION CORPORATION OF ANDHRA PRADESH LIMITED (here in after called ‘APTRANSCO’) accept the offer of  M/s. Larsen & Toubro Limited (here in after called ‘Contractor’) under reference (2) cited read along with subsequent correspondence together with their letters under reference (3) cited and APTRANSCO’s bidding documents for Bid No. e-EHVT-10/2013 for Design, Engineering, Civil & Construction works, Erection, Testing and Commissioning for execution of 400kV QMDC Line  from existing 400kV SS Veltoor to YEMMIGANOOR(Common point) of a length of  95.24 kM (Approx.),  is hereby accepted for a total amount Rs. 52,00,50,148.00 (Rupees Fifty Two Crores ,Fifty Thousands, One Hundred and Forty Eight only) as detailed in Schedule - II enclosed  subject to the conditions set out in this order. This is issued in regularization of Letter of Intent (LOI) communicated in the reference (4) above and your acceptance of the same under reference (5) cited.

- SCOPE:

The Scope of this order covers Design, Engineering, Civil & Construction works, Erection, Testing and Commissioning of following items required for execution of 400kV QMDC Line  from existing 400kV SS Veltoor to YEMMIGANOOR(Common point) of a length of  95.24 kM (Approx.) on Turnkey Basis as detailed below:

- Design of specific towers/extensions/strengthening if required in the project at no additional cost including detailing, proto testing, furnishing of Bill of Material  (BOMs) drawing etc. All the relevant drawings  in AUTO CAD to the scale  with reproducible tracings in such cases shall also be supplied to the purchaser by the successful bidder at free of cost.

- The new tower/ extensions if any, including detailing, proto testing, furnishing of Bill of Material (BOMs) drawing etc shall be developed and got approved by CPRI, Bangalore.

- Detailed survey (if and where required), check survey,  Soil Investigation, laying of Pile/Conventional foundations, river crossing works, developing stringing charts, erection,  testing and commissioning of the 400kV DC transmission line employing Quad Moose bundled ACSR conductor per phase and one no. 7/3.66 mm GSS earth wire and 1 No. OPGW.

- Cutting & removing of all kinds of trees of all girths & all sizes and also clearing of scrub jungle including transportation and disposal along the route of the line for a total corridor of 52 mtrs.

Also the contract is on TURN KEY basis and hence any other items not specifically mentioned in the specification but which are required for erection, testing & commissioning and satisfactory operation of this  line are deemed to be included in the scope of the contract and same shall be arranged by the contractor unconditionally.

The rates indicated in Schedule- II appended to this order are for Erection works.

- ABSTRACT of Schedule:

| Sl.No. | Item Description | Amount (in Rs.) |
| --- | --- | --- |
| 1 | SCHEDULE OF PRICES FOR CIVIL, CONSTRUCTION,ERECTION, TESTING AND COMMISSIONING WORKS (Schedule- II) | Rs. 52,00,50,148.00 |
| (Rupees Fifty Two Crores, Fifty Thousands, One Hundred and Forty Eight only) |  |  |

3.0      PRICES AND PRICE ADJUSTMENTS:

For Erection works:

3.1     The accepted rates for the items except for cement & reinforcement steel, shall be firm on all accounts such as (i) increase in quantum of work provided in the contract, (ii) execution of contract beyond the scheduled completion period for whatever reasons, (iii) increase in the rates of material and labour both during and beyond the completion period etc., These prices shall include all the taxes and duties wherever applicable. Price variation is applicable for items cement, reinforcement steel as per Price Variation clause mentioned at Annexure.

## 3.2   The quantities stated in price schedule are approximate only and unit price shall apply to actual quantities measured on the completed work in accordance with specification and drawings.

Any other items not specifically mentioned in the bidding documents / drawings  but which are required for Erection, Testing and Commissioning of 400 kV line  are deemed to have  been  included in the scope of the contract as mentioned in tender specification. The above prices include insurance to be covered by the contractor for the works, workmen’s compensation, and all other insurances required as per tender specification.

4.0	TAXES AND DUTIES:

Erection items:

4.1	 The erection prices are inclusive of all taxes like APVAT/ WCT @ 5 %,                     Service tax @ 12.36 %, Labour Welfare Cess @ 1 % etc.

4.2	The Contractor will be entirely responsible for payment of taxes and duties, other local taxes or levies if any, license fee, etc., which are to be borne by the company/contractor until the completion of the contract.

4.3	No claim against the variation in taxes and duties or new levies in respect of the transaction between the Contractor and their vendors / sub-suppliers while procuring any components,                 sub-assemblies, raw materials and equipment will be entertained by the APTRANSCO.

4.4	Purchaser shall not bear any tax liability ie., Income Tax, surcharge on Income Tax and any other Corporate Tax, irrespective of the mode of contracting. The contractor shall be liable and responsible for payment of taxes, under the provision of the law. The Purchaser as per the respective acts will make deduction towards Income Tax, APVAT/WCT, Service tax and Labour cess at source.

4.5	    APTRANSCO is registered as a dealer under APVAT act, TIN No.28760127045.

4.6	PAYMENT OF TAXES, LEVIES, DUTIES, STATUTES

4.6.1   Contractor shall be entirely responsible for payment of all taxes, levies, duties, other local taxes, license fees, etc.,

4..6.2    The contractor shall pay all types of fees, levies, taxes, duties etc. required to be paid by any National or State statute, ordinance or other law or any regulation or bye-law of any local or other duly constituted authority in relation to the execution of works and by the rules and regulations of all Public bodies and companies whose property or rights are affected in any way during the execution of works. In compliance to the above, the contractor shall keep the Purchaser indemnified against all such penalties and liability of every kind for breach of any statute, ordinance or law, regulation or byelaw.

4.6.3   	Nothing in the contract shall relieve the contractor from his responsibility to pay any tax that may be levied by the Government on the turnover / profits made by him in respect of the contract.

4.7	TAX AND CESS DEDUCTABLE AT SOURCE:

4.9	As per provision of APVAT/WCT, Service tax and Income tax Act, applicable taxes will be deducted at source at all stages of payment of the bills and same will be remitted to the concerned department as per the rules / acts of the State / Central Government. The present rates of the TDS are Income Tax @ 2.0%, Works Contract Tax @ 5%,  Labour Cess @ 1% on Work bills. However, the deductions will be made as per the rates prevailing as on the date of billing.

4.8     SERVICE TAX ON LABOUR PORTION OF THE WORKS :

(1)	The Service provider has to raise the Invoice with Service Tax showing the clear breakup of liability to both the Service provider (Contractor) as well as Service recipient (APTRANSCO) in terms of reverse charge mechanism separately.

(2)	The Service provider has to discharge his portion of liability and APTRANSCO will reimburse only on submission of proof of such payment.

(3) (i)	APTRANSCO liability as service receiver under reverse charge mechanism starts from the date of making payment to the Service provider if the payment is made within a period of 6 months from the date of Invoice.

(ii)	Where the payment is not made within a period of six (6) months from the date of invoice, APTRANSCO liability will be from the date of completion of service.

4.9   SEINORAGE CHARGES:

Seignorage charges shall be paid to the Assistant Director Mines & Geology Department as per existing rules in vogue.

4.10	STATUTORY VARIATION :

Any variation increase or decrease in statutory levy or new levies introduced after issue of the Contract award letter under this specification will be to the account of APTRANSCO on production of documentary evidence provided the variation is within the scheduled completion  period of contract. This is allowed only once during delivery period i.e at the time of delivery of goods at factory.

In cases where the Contractor does not adhere to schedule of programme of works and if there is any upward variation/revision in taxes & duties after the  agreed schedule of programme of works, the Contractor shall bear such impact of levies and if there is any downward variation/revision, the credit shall be passed on to APTRANSCO to that extent irrespective of scheduled completion of period of contract.

Any variation increase or decrease in taxes and duties, or new levies introduced subsequent to bid closing and before contract award shall be regulated in the contract agreement by the agreement concluding authority.

In case of sub-vendor items, Taxes and Duties shall be inclusive in accepted price and no statutory variation is applicable. Further, price variation if any indicated in Bid document in respect of sub-vendor items will be considered on accepted prices.

5.0	DELIVERY / COMPLETION PERIOD:

Erection works shall commence at least  in third  week of  Third (3rd) month from the date of handing over of detailed survey profiles .However the contractor is advised to commence  the work immediately and complete (in full shape) the Erection, Testing & Commissioning within Eighteen (18) months from the date of  handing over of detailed survey profiles

6.0	TERMS OF PAYMENT FOR ERECTION:

6.1	The payment will be made through Bank/Funding agency.

Payments for the erection will be made up to 90 % of the monthly bills at the rates approved in the schedules for the items of work done.  For this purpose the Contractor shall submit monthly bills to the Executive Engineer regularly to ensure payments in time.  The Contractor shall give full details of items of works done against each location in support of the bill.  Bills submitted without supporting details will not be taken into cognizance.

Out of the balance 10% amount, 5% payment will be released after completion of all works & upon submission of material account, provided if all the works including testing & commissioning of the line are completed and the same is certified by the purchaser.

The balance final 5% will be paid after completion of one year performance guarantee period reckoned from the date of completion of all the works as per contract or after all the balance materials leftover after completion of works are handed over to the APTRANSCO, which ever is later. The date of commissioning/energizing the line will not be considered for reckoning the purchase guarantee period.

6.2    	In case, the balance materials are returned to APTRANSCO well before the completion of the performance guarantee period, the 5% amount will be released against an additional bank guarantee for equal amount, which shall be valid for the performance guarantee period and also provide six months claim period. “All banking charges should be to the account of the Contractor”.

7.0    FINAL PAYMENT:

Whenever, in the opinion of owner, the work covered by the Contract has been completed, he shall prepare a final abstract showing the total amount of work done by Contractor and its value under and according to the terms of the Contract.  From the total value thus arrived at shall be deducted all previous payments and all deductions made in accordance with the provisions of the Contract.  The remainder shall be paid by owner to Contractor within three months after the date of owner’s final certificates.

7.1   Where the Vendor/Contractor requests for the payment in advance before the “ scheduled date of payment” would be examined by the negotiations committee to decide whether such facility could be extended or not and if found acceptable the Contractor should agree to offer a rebate/ discount @ 0.3% per week or part there of for the advancement.  Based on the decision, the Finance & Accounts wing will release priority payment to such Contractor after availing of the rebate/ discount.

7.2	The payment for super-structure erection shall be based on the calculated weights of tower and their extensions as per the approved bill of material for each type of tower.

7.3      The payment for excavation and concreting shall be based on the approved design volumes of excavation and concreting.

7.4 	No claim for idle period resulting from any "Force Majeure" condition shall be entertained by the purchaser.

7.5    RTGS/NEFT MANDATE FORM as per the letter submitted by M/s L&T vide dated            30-11-2013

| a) | Name of the Bank | : | Citi Bank N.A. |
| --- | --- | --- | --- |
| b) | Name of the Branch and Address of the Customer | : | Mumbai Branch, Bombay Mutual Building, Dr. D.N.Road, Fort, Mumbai – 400001. |
| c) | 9 – digit MICR code number of the Bank & Branch | : | 400037002 |
| d) | Type of Account | : | Current Account |
| e) | Account Number | : | 0015963107 |
| f) | RTGS IFSC Code | : | CITI0100000 |
| g) | NEFT Code | : | CITI0100000 |

8.0  	PERFORMANCE SECURITY:

8.1	The Contractor shall furnish the following ‘Performance Security’ Bank guarantees within 15 days of issue of letter of intent (LOI) from purchaser as per Clause.39.0 of ITB, Vol-I of the tender specification.

Bank Guarantee towards Performance Security (Erection) for an amount equivalent to 5% of erection value i.e., Rs. 2,60,02,510.00 valid up to 30.06.2016 and claim period up to 31-8-2016.

  - The Performance Security/additional performance securities shall cover the 12 months  over   and above completion period, with a further claim period of two months thereafter.

  - Performance security may in the form of

(i) 	A Bank Guarantee from any Scheduled Bank (list specified) as per list under  Section-7 State Bank of India or its associate banks/ Nationalized banks in favour of Chief Engineer / Construction / 400kV.

(ii) 	A Banker cheque, crossed Demand Draft, pay order on any Nationalized Bank / Scheduled Bank/ State Bank of India or its associate banks in the Headquarters in favour of Pay Officer/APTRANSCO.

  - The Bank guarantee for Performance Security should be extended suitably in case the equipment is found defective and not attended to within the performance guarantee period or any other contractual obligations are not fulfilled. The purchaser will discharge the Performance Security after completion of the contract and within 60 days of the expiry of the warranty.

9.0	INDEMNITY BOND FOR ALL MATERIALS

For all materials supplied by the Contractor and through the sub-vendors, the Contractor shall take delivery of materials after executing an indemnity bond in favour of the Purchaser against loss, damage and any risks involved, for the full value of the materials.  This indemnity bond shall be valid till the scheduled date of testing, commissioning and handing over of the line to the Purchaser.

10.0   CONTRACT AGREEMENT

10.1   The Contractor shall enter into a Contract Agreement in the prescribed proforma as indicated in Annexure X of Volume-I of bidding documents with the Purchaser within thirty (30) days from the date of “Notice  of  Award of Contract" or within such extended time as may  be  granted  by the Purchaser.

10.2  The agreement shall be executed at the Office of the Chief Engineer Construction 400kV, APTRANSCO, Vidyut Soudha, Hyderabad on a date and time to be mutually agreed.

The expenses for the preparation and stamping the contract agreement shall be to the account of the Contractor.

11.0 	WARRANTY/GUARANTEE:

ERECTION:

Twelve (12) calendar months from the date of completion of the contract, unless otherwise agreed in writing by Purchaser, will be deemed to be the 'Defect Liability Period'.  The works shall not be considered as completed until Owner has certified in writing that they have been virtually completed and the defects liability period shall commence from the date of such certificate.  In case any defects in the work due to bad materials, and/or bad workmanship develop in the work before the expiry of the period, the contractor, on notification by Purchaser shall rectify or remedy the defects at his own cost and he shall make his own arrangements to provide materials, labour, equipment and any other appliances required in this regard. The performance security will be returned to contractor only after the expiry of this defect liability period.  In case even on due notification by purchaser, the contractor fails to rectify or remedy the defects, purchaser shall have the right to get this done by the other agents and recover the cost incurred by deductions from the retention amount due to the contractor, in case this cost is within the value of the performance security, and if not, contractor shall be liable to pay to purchaser the balance amount.

The provisions of this clause shall apply to all replacements or renewals carried out by the contractor as if the replacements or renewals had been taken over on the date they were completed.

The Defects Liability period for the works shall be extended by a period equal to the period during which the works cannot be used by reason of a defect or damage. If only part of the works is affected the Defects Liability period shall be extended for that part.  In neither case Shall the Defects Liability period be extended by more than one year.

12.0 	FORCE MAJEURE

12.1	Force majeure is herein defined as

- Any cause which is beyond the control of contractor or Purchaser, as the case may be

- Natural phenomenon including but not limited to weather conditions, floods, drought, earthquakes and epidemics.

- Acts of any governmental authority, domestic or foreign, including but not limited to war, declared or undeclared, priorities, quarantine, embargoes, licensing control or production or distribution restrictions.

- Accidents and disruptions including but not limited to fires, explosions, breakdowns of essential machinery or equipment and power shortages.

- Transportation delay due to force majeure or accidents.

- Strikes, slowdown, lockouts and sabotage.

- Riots and civil commotions.

  - If a Force Majeure situation arises, the supplier/contractor shall promptly notify the Purchaser within 10 days in writing of such condition and the cause thereof.  Unless otherwise directed by the Purchaser in writing, the supplier/contractor shall continue to perform its obligations under the contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event.

  - The Contractor or the purchaser shall not be liable for delays in performing his obligations resulting from any force majeure cause as referred to and/or defined above.

  - Notwithstanding the provisions of clauses 12.1, 12.2, 12.3, the supplier/contractor shall not be liable for forfeiture of its performance security, penalty for late delivery or termination for default, if and to the extent that, its delay in performance or other failure to perform its obligations under the contract is the result of an event of force Majeure.

  - No price variance is allowed during the period of Force Majeure Conditions.

13.0	PENALTY FOR ERECTION :

13.1	The time stipulated in the contract for the execution and completion of the works shall be deemed to be the essence of the contract. In the event the contractor fails to execute, complete and deliver the works within the time specified in the contract, then the contractor shall pay to Purchaser as and by way of penalty an amount equal to Half percent (1/2%) of the value of the unperformed services for each week's delay beyond the date of completion specified in the contract. However, such payments shall not exceed 10% of the total value of the contract. Purchaser may, without prejudice to any method of recovery, deduct the amount for such damages from any amount due or which may become due to the contractor. In the event of extension of time being granted by Purchaser in writing for completion of the work, stated in Clause No.7.0 of GCE, Volume-I of the specification, this penalty clause will be applicable after the expiry of such extension period.

In case of non-achievement of Targets of the scheduled works by the Contractors when compared with the PERT charts as accepted in the Kickoff meetings, whatever may be the reasons, the APTRANSCO shall levy and collect the penalty @ 1% per month of value of non-achieved targets fixed in the Kickoff meeting. However if the work is completed within the total scheduled completion period the penalty recovered so i.e penalty recovered towards non-achievement of Targets  by the Contractors when compared with the PERT charts as accepted in the Kickoff meetings shall be released.

However, as these are fast track projects the performance of the company will be monitored very rigorously  and action will be initiated on the companies as indicated below:

- After completion of first 3 months of work period the progress will be monitored with respect to the pert chart furnished during the kickoff meeting.  If the company has not completed 30% of the erection works, a penalty @ 5% of value of the balance works to have been done in the said 3 months will be deducted from their progressive bills.

- After completion of 6 months of work period the progress will be monitored with respect to the pert chart furnished during the kickoff meeting.  If the company has not completed 50% of the erection works, a penalty @ 5% of value of the balance works to have been done in the said 6 months will be deducted from their progressive bills.

- After completion of 9 months of work period the progress will be monitored with respect to the pert chart furnished during the kickoff meeting.  If the company has not completed 70% of erection, the contract awarded to them will be liable for termination without any further notice to the company.

  - PENALTY FOR DEFICIENCY IN QUALITY OF WORKS

It has been observed that while executing the EHT line/ Sub-station works, certain lapses or omissions are being committed by the contractors, which have an effect on the stability of the line or structure.  To prevent such lapses on the part of the contractors and bring about greater awareness on their part it is proposed to levy a penalty on the defaulting contractors.

The following instructions are therefore issued in this regard for strict adherence by officers to ensure Quality of works in execution of transmission lines and Substations in the field.  In case any deficiency in quality of works is found during the course of execution of works and any category wise deficiency in quality of works, APTRANSCO will impose penalty and take other actions as indicated below:

| S. No. | Deficiency in quality from the specification/ Agreement such as | Instance wise Minimum penalty leviable in Rupees during the same work by the contractor |  |  | Duration of disqualification of the contractor for participation in the tenders of APTRANSCO in the event of further instance. |
| --- | --- | --- | --- | --- | --- |
|  |  | 1st Instance | 2nd Instance | 3rd Instance |  |
| Category-I | Not using (i) prescribed shoring, shuttering and dewatering equipment (ii) measurement boxes, (iii) form boxes for steel measuring boxes, (iv) not providing adequate number of chairs to the steel reinforcements, (v) not carrying out back filling and compaction of the foundation pits in layers and leveling the tower footings properly, (vi) not ensuring that the excavated earth is dumped at least 2 meters away from the pit etc., (vii) not providing coping to tower leg/stubs and (viii) not providing water tanker, Earth rammers/ Earth vibrators. | 5000 | 10000 | 15000 | Debarred from participating in future tenders for a minimum period of one year |
| Category-II | Use of reinforcement steel without ISI marking, not using vibrators for effective consolidation of the concrete during foundation works, not using proper templates for firmly keeping the stubs in position when templates are supplied by the contractor and improper fixing of stubs, non ensuring of tower verticality, use of rusted stubs and tower parts if supply is by the contractor, non painting of butt joints and rusted stubs with zinc rich paint immediately after erection of the towers and stringing, non fixing of earth flat to the stub, non deployment of technical personnel for supervision of works by the contractor. | 7500 | 15000 | 22500 | Debarred from participating in future tenders for a minimum period of one year. |
| Category-III | Use of improper grade/quality of raw material like HBG metal, water and sand for concreting using clogged and/or lump/ clotted cement for concreting not ensuring proper curing for foundation concrete, not ensuring that all the members of the tower are placed in position and firmly fixed with bolts and nuts immediately after erection of tower. | 10000 | 20000 | 30000 | Debarred from participating in future tenders for a minimum period of one year. |

14.0  Incentives for early completion of the works:

The contractors who completes the transmission line works well before the scheduled completion period will be awarded incentives as per the formula given below :

Incentive Bonus Formula.

I = Z * {Y/(X/3)} * 4%,

Where,

I   =       Incentive Bonus,

Z   =      Project cost

Y   =     Days equivalent to the difference of the Scheduled Project commissioning

date and the actual Project commissioning date.

X =       Time period in days for completion of a Project specified in the

Specification / bidding documents of the Project.

However Y should be > 30 days and Incentive Bonus is limited to 4% of the Project Cost.

15.0   INSURANCE FOR ERECTION :

15.1	In addition to the conditions covered under the clause entitled ‘Insurance’ in ‘General Conditions of Contract’, the following provisions will apply to the portion of the 'Works' to be done beyond the CONTRACTOR's own or his SUB-CONTRACTOR's works. Comprehensive Insurance of equipment/materials during erection and commissioning, Workmen's Compensation Insurance, Comprehensive Automobile Insurance and Comprehensive General Liability Insurance shall be the responsibility of the CONTRACTOR. The Contractor shall at his own expense arrange to effect and maintain until the completion of the contract, Insurance policies, with an insurance company approved by Purchaser, against all risks in respect of which contractor is required under this clause to indemnify purchaser. In  particular, the Contractor shall effect and maintain an insurance policy of at least Rs.3.00 lakhs for one person and Rs.5.00 lakhs per accidental for injury or death and at least Rs.5.00 lakhs per accident for third party property damage, to indemnify purchaser against all third party accident/damage claims which may arise in respect of the work or in consequence thereof. The Contractor shall also maintain an insurance policy against all claims which may be made upon Purchaser whether under the Workmen's Compensation Act or any other statue in force during the currency of the contract or at common law in respect of any employee of contractor or any sub-contractor. All such insurance policies shall be in the joint names of purchaser and contractor and shall be deposited with purchaser.  The Contractor shall be responsible for anything which may be excluded from the insurance policies referred to above and also for all other damage to any property or persons out of and incidental to the negligence or defective carrying out of this contract.

All costs on account of insurance liabilities covered under the contract will be on the contractor's account and will be deemed to have been included in the contract price.

15.2	Workmen's Compensation Insurance:

This insurance shall protect the CONTRACTOR against all claims applicable under the Workmen's Compensation Act, 1948 (Government of India). This policy shall also cover the CONTRACTOR against claims for injury, disability, disease or death of his or his SUB-CONTRACTOR's employees, which for any reason are not covered under the Workmen's Compensation Act, 1948.  The liabilities shall not be less than :

Work Men’s compensation	-	As per statutory provision

Employees liability		- 	As per statutory provision.

  - Comprehensive Automobile Insurance:

This insurance shall be in such a form to protect the CONTRACTOR against all claims for injuries, disability disease and death to members of public including the PURCHASER's men and damage to the property of others arising from the use of motor vehicles during on or off the 'Site' operations, irrespective of the purchaser-ship of such vehicles.

The liability covered shall be as herein indicated:

Fatal injury		:  Rs.  1,00,000 each person

Rs.  2,00,000 each occurrence

Property damage	:  Rs.  1,00,000 each occurrence

15.4    Comprehensive General Liability Insurance

This insurance shall protect the CONTRACTOR against all claims arising from injuries, disabilities, diseases or death of members of public or damage to property of others due to any Act or omission on the part of the CONTRACTOR, his agents, his employees, his representatives and SUB-CONTRACTORs from riots, strikes and civil commotion. This insurance shall also cover all the liabilities of the CONTRACTOR arising out of the clause entitled 'Clause. 32.0’ of GCC Indemnify the Purchaser under 'General Conditions of Contract'.

15.5 	The hazards to be covered will pertain to all the works which and areas where, the CONTRACTOR, his SUB-CONTRACTOR, his agents and his employees have to perform work pursuant to the 'Contract'.

  - The above are only illustrative list of insurance covers normally required and it will be the responsibility of the CONTRACTOR to maintain all necessary insurance coverage to the extent both in time and amount to take care of all his liabilities either direct or indirect, in pursuance of the 'Contract'.

15.7   Fire Insurance:

Unless otherwise instructed by the PURCHASER/ENGINEER, the CONTRACTOR shall, on signing the 'Contract', insure the works and keep them insured until the completion of the 'Contract' against loss or damage by fire, with the Company to be approved by the PURCHASER/ENGINEER, in the joint names of the PURCHASER and the CONTRACTOR for such amount and for any further sum, if called upon to do so by the PURCHASER/ ENGINEER, the premium of such further sum being allowed to the CONTRACTOR as an authorised  extra.  Such policy shall cover the property of the PURCHASER only and shall not cover any property of the CONTRACTOR or any SUB-CONTRACTOR, or his employees.  The CONTRACTOR shall deposit the policy receipts for the premium with the PURCHASER/ENGINEER within twenty one (21) days from the date of signing the 'Contract' unless otherwise instructed by the PURCHASER/ENGINEER.

In default of the CONTRACTOR insuring as provided above, the PURCHASER may so insure and may deduct the premiums paid from any moneys due, or which may become due to the CONTRACTOR.  The CONTRACTOR shall, as soon as the claim under the policy in settled, or the work reinstated by the insurance office should they elect to do so, proceed with all due diligence with the completion of the 'Works' in the same manner as though the fire had not occurred and in all respects under the same conditions of 'Contract'. The CONTRACTOR in case of rebuilding or reinstalment after fire, shall be entitled to such extension of time for completion as the PURCHASER/ENGINEER may deem fit.

15.8     Comprehensive transport, storage, erection cum commissioning insurance:

15.9  	 All the equipment and materials being supplied by the Contractor shall be kept completely insured by the Contractor at his cost from the time of despatch from the Contractors Works, upto the completion of erection, testing and commissioning at site and taking over the works by the Purchaser in accordance with the contract.

15.10  The Contractor shall inspect all the material received at destination store and furnish a loss/damage report to Purchaser within a week of receipt of material at site, and provide all required assistance to Purchaser in lodging insurance claims thereupon.  In case of loss to Purchaser due to delays in submitting the loss/damages report by the contractor, Purchaser will be within his right to deduct such losses from the contractor's progressive payments. All the equipment and materials being supplied by the Purchaser shall be kept insured by the contractor against loss, damage, theft, pilferage, fire etc., from the point of unloading upto the time of taking over of the works by the purchaser including handling, transportation, storage, erection, testing and commissioning etc., and the contractor shall be fully responsible for making good of any loss or damage at his own cost.  All costs for such insurance shall be to the contractor account and shall be deemed to be included in the contract price.

15.11  It will be the responsibility of the Contractor to lodge, pursue and settle all claims with the Insurance Company in case of any damage, loss, theft, pilferage or fire and the Purchaser shall be kept informed about it.  The losses, if any, will have to be borne by the Contractor, if the claims are not lodged and pursued properly or in time or if the same are not settled by the insurance company.  The contractor shall replace the lost/damaged materials (own and the Purchaser's supplied) promptly irrespective of the settlement of the claims by the underwriters and ensure that the work progress is as per agreed schedules. The losses, if any, in such replacement will have to be borne by the contractor.

16.0	SECURITY (WATCH & WARD)

The CONTRACTOR shall have total responsibility for all equipment and materials in his custody stored, loose, semi-assembled and/or erected by him at 'Site'. The CONTRACTOR shall make suitable security arrangements including employment of security  personnel to ensure the protection of all   materials, equipment and 'Works' from theft, fire, pilferage and any other damage and loss.

17.0   VARIATION IN QUANTITIES AND RATES :

For work items covered in Schedule :

- For quantities increased up to 50% over and above the Scheduled quantities:  The rates accepted for individual items shall hold good up to 50% over and above the agreement quantities.

- For quantities increased beyond 50%over and above the Scheduled quantities:  The rates payable for the quantities beyond 50%over and above the agreement quantities will be APTRANSCO estimated rate or accepted rate whichever is less.

18.0  PURCHASER’S RIGHT TO VARY THE SCOPE DURING THE PERIOD OF CONTRACT:

Purchaser may change the scope of the Contract based on the priorities and may subsequently extend for balance scope with the prices quoted if required.

Purchaser reserves the right to increase or decrease the scope stated above as per requirement up to (+) or (-) 50% during the execution of the order with the quoted prices.

19.0    QUALITY ASSURANCE PROGRAMME

The contractor shall submit quality plan for the works to be carried out indicating the procedures and quality control activities and got approved prior to commencement of erection works. However, this shall not relieve the contractor of any of his contractual responsibilities under the contract.

- 20.0    KICK – OFF MEETING :

- The Kick off meeting shall be held by Chief Engineer / 400 kV Construction. The targets are to be fixed in the kick-off meeting, which shall be signed by both APTransco and the contractor and shall become a part of the contract. The targets fixed in the kick-off meeting are final and the progress shall be reviewed periodically.

- The Contractor or his representative shall invariably attend the meeting whenever called. The representative of the contractor who attends the kick-off meeting and review meetings shall be qualified and shall be authorized by the contractor with details of qualification, responsibility and designation of the authorized person.

21.0   INCIDENTAL SERVICES

  - As specified in the relevant bid documents the Supplier/ Contractor may be required to provide any or all of the following services: -

        - Performance or Supervision of on site assembly and / or start up of the supplied material / equipment.

        - Furnishing of tools required for assembly and/or maintenance of the supplied Goods;

        - Furnishing of a detailed operations and maintenance manual for each appropriate unit of the supplied Goods;

        - Performance   or supervision or maintenance and/or repair of the supplied Goods, for a period of time agreed upon by the parties, provided that this service shall not relieve the Supplier of any warranty obligations under this Contract; and

(e) Training to the Purchaser’s personnel, at the Supplier's plant and/or on site, in assembly,         start-up, operation, maintenance and/or repair of the supplied Goods.

21.2  	Prices charged by the Supplier for the above incidental services, should be included in the contract price and any extra changes will not be considered.

22.0  SUPPLEMENTAL/NEW ITEMS AND PROCEDURE FOR WORKING  OUT        	RATES.

The Contractor is bound to execute all supplemental items that are found essential, incidental and inevitable during execution of the contract at the rates to be worked out as below: -

22.1  	SUPPLEMENTAL ITEMS /NEW ITEMS

i) 	For the items relating to the Schedule-II where the rate can be deduced from the estimate or APTRANSCO / DISCOMS / common SSR, the rate applicable will be the estimated / SSR rate +/- tender percentage quoted/ accepted by the Contractor for Schedule –II.  The schedule of rates adopted for supplemental items / new items shall be from the current SSR applicable during the execution period.

ii) 	For the items relating to the Schedule where the rates of new items cannot be deduced from the estimate / SSR, the rate payable will be arrived based on the prevailing market rates duly enquiring / collecting quotations and observing the reasonableness of the rates by the Purchaser

22.2 	The contractor shall plan and procure the materials indicated in the schedule ‘I’ duly verifying with the approved layout and profile so that the procured quantities match with actual requirement to avoid excess supply of materials. The Executive Engineer shall give the details of the materials such as quantities of type wise towers and extensions and other line materials based on the line approved profile and the quantities of type wise structures and other materials based on the approved layout on the date of Kickoff meeting without fail.

22.3   The Schedule time required to complete the new / supplemental items including the balance work will be indicated in the approval letter issued for new / supplemental items.

23.0	PHOTOGRAPHS AND PROGRESS REPORT

23.1 Contractor shall furnish three (3) prints to the PURCHASER/ENGINEER of progress photographs of the work done at 'Site'.  Photographs shall be taken when and where indicated by the PURCHASER/ENGINEER or his representative.  Photographs shall be adequate in size and number to indicate various stages of erection.  Each photograph shall contain the date, the name of the CONTRACTOR and the title of the photograph. Normally photographs may be taken once every 15 days and for all special events.

  - The above photographs shall accompany the fortnight/ monthly progress report detailing out the progress achieved on all erection activities as compared to the Schedules. The report shall also indicate the reasons for the variance between the scheduled and actual progress and the action proposed for corrective measures wherever necessary. The contractor shall furnish progress reports as and when requested by the PURCHASER/ ENGINEER.

23.3  Photographs shall be taken by the contractor for each tower location of EHT lines in the  following stages of

- After excavation is over in normal soils.

- Before and after blasting in Hard rock soils.

- During dewatering.

- During concreting.

- Shoring & strutting.

The photographs should be clear. The Contractor shall submit both hard copy and soft copy (2 sets) to the Engineer in charge immediately.

24.0	TREE/CROP COMPENSATION,RIGHT-OF-WAY, CUTTING OF TREES, ETC.

24.1	Payment of compensation for damaged crops or fruit bearing trees shall be initially made by the contractor, which will be reimbursed by APTRANSCO later on. The compensation so payable in respect of damaged crops shall be based on the assessment of MRO.  In respect of the trees, compensation so payable is the lowest of the rates fixed by the Horticulture/NABARD/MRO. The contractor shall take up the payment of compensation amount only after written approval by the Executive Engineer.  The payment shall be made in the presence of representatives of 400kV, Accounts and Vigilance wings of APTRANSCO.  The Superintending Engineer/ 400kV shall finalise the compensation claims.

  - The contractor shall take all possible steps to see that standing crops etc. are not damaged during execution of works.  When such damage is inevitable, the compensation will be borne by the APTRANSCO to the extent of land required for laying of foundation, provided the damage is with prior concurrence of the Executive Engineer.  The contractor shall bear the compensation for damages caused without prior concurrence of the Executive Engineer concerned.  Any extra land required by the contractor temporarily for dumping of the construction material and consequent damage to the crops etc. shall be the responsibility of the contractor.

  - In the event of any obstruction being encountered from the local villagers of authorities, the contractor shall immediately notify the Executive Engineer who shall take such steps as may be necessary to clear the obstruction.  The contractor or his representative or gangs shall not adopt antagonistic attitude towards the village authorities with whom they may come into contact, but shall immediately report to the Executive Engineer any case of obstruction which cannot be settled amicably.  No trees shall be cut until the APRTANSCO has made necessary arrangement with the authorities concerned and permission is given to the contractor to fell such trees.  The APTRANSCO shall arrange to remove the obstacles as soon as possible.  At times however, it may not be possible for the APTRANSCO to arrange right-of-way for laying foundations or erecting the towers or stringing the line.  At all such times, the contractor shall shift his gangs to other locations.  The rates quoted shall cover all such contingencies and no extra payments shall be claimed for such contingencies

24.4 	The APTRANSCO will arrange the right-of-way along the transmission line route. Any avoidable or deliberate damage done to standing crop or private property by the erection contractor’s labourers shall be the erection contractor’s responsibility.

The erection contractor shall take all reasonable steps for preventing damage to crops during execution of the contract work.

Clearing of obstructions falling in the right-of-way as per IS:5613  (part-2, section-2) –1985 and lopping or trimming of the portion of the trees falling within the minimum electrical clearance zone shall be the responsibility of the contractor. And also, any lopping or trimming of tree branches obstructing the line of sight during check survey shall be the responsibility of the erection contractor.

25.0     SURPLUS MATERIALS:

On completion of the works material account shall be settled and all surplus materials handed over to the contractor for erection shall be returned to the Engineer by and at the expense of the contractor in the Purchaser's store(s) itself.

- The contractor within two (2) months from the date of completion of the line (ready for charging) shall return and account for the surplus materials, if any otherwise the material is deemed to be sold to the contractor at DOUBLE the rate of issue of material and recoveries shall be effected in the contractor’s Bills accordingly.

26.0    CORRESPONDENCE:

All the correspondence regarding the works / payments and other field matters shall be addressed to the Superintending Engineer/400kV L& SS/Vijayawada with copies marked to this office.

All the correspondence on all the technical matters shall be addressed to this office with   copies marked to the Superintending Engineer/400kV L& SS/Vijayawada.

27.0    GENERAL CONDITIONS OF CONTRACT:

- Except in so far as it is provided otherwise in this contract, all the general, technical,     commercial terms and conditions stipulated in the bidding documents for this contract shall be complied with.

28.0	DESIGN AND DRAWINGS:

The structural drawings for towers and their foundations shall be provided by the Purchaser. Wherever the drawings and designs are provided by APTRANSCO, the suitability of these design and drawings shall be verified by the Contractor for design requirements as per standards, site and soil conditions based on the soil investigation and furnish the detailed design verification calculations before execution if sought by APTRANSCO. Standard BOMs for towers, stubs will be communicated to the contractor after placement of Purchase Order. Substitutions if any of steel sections of the tower parts with higher size due to non-availability or otherwise, shall be to the contractors account. The purchaser will not accept any liability on this account. The supplier/contractor shall raise the invoices as per standard BOMs. In case of minor variation in BOM approved after proto inspection, only the approved standard BOM will be invoiced and paid.

  - Where design of a particular tower extension / leg extension is not available with the purchaser or where any modification in the design or new design is required, the contractor shall have to design the same to APTRANSCO at no additional cost, including detailing, proto testing, furnishing of Bill of Material (BOMs) drawing etc.  All the relevant drawings along with reproducible tracings in such cases shall also be supplied to the purchaser by the contractor  at free of cost.

  - The scope of work also includes redrawing of existing structural and shop drawings of all the towers being used in the project using AutoCAD duly certifying their correctness and to be handed over to APTRANSCO in hard and soft copies.

29.0     SUSPENSION, TERMINATION BY PURCHASER FOR CONVENIENCE

29.1	The Purchaser reserves the right to suspend and re-instate execution of the whole or any part of the 'Works' without invalidating the provisions of the 'Contract'. Orders for suspension or reinstatement of the 'Works' will be issued by the Purchaser or Engineer to the Contractor in writing.  The time for completion of the works will be extended suitably to account for duration of the suspension.

29.2  	 Any necessary and demonstrable cost incurred by the Contractor as a result of such suspension of the 'Works' will be compensated by the Purchaser provided such costs are substantiated to the satisfaction of the Purchaser or the Engineer. The Purchaser shall not be responsible for any liabilities if suspension or delay is due to some default on the part of the Contractor or his sub-Contractor or due   to   force   majeure conditions.

  - The Purchaser may, by a written notice sent to the supplier/ contractor terminate the contract, in whole or in part, at any time, for its convenience.  The notice of termination shall specify that termination is for the Purchaser's convenience, and extent to which performance of work under the Contract is terminated, and the date upon which such termination becomes effective.

  - The goods and services that are complete and ready for despatch shall hand over within 30 days after the supplier's/contractor’s receipt of notice of termination shall be purchased by the Purchaser at the contract terms and prices.  For the remaining goods, the purchaser may select to have any portion completed and delivered at the contract terms and prices.

  - In the event of any dispute in regard to the price of the 'Works' and portion of the payment to be made to the CONTRACTOR, the decision of the Purchaser shall be final.

  - The CONTRACTOR will be further required to transfer the title and provide the Purchaser with the following, in the manner and as directed by the Purchaser:

- Any completed 'Works'.

- Such partially completed ‘Works’ including drawings, information’s and contract rights as the CONTRACTOR as specifically performed, produced or acquired for the performance of the 'Contract'.

30.0	TERMINATION FOR DEFAULT

30.1    	The purchaser may, without prejudice to any other remedy for breach of contract, by written notice of default sent to the supplier/ Contractor, terminate the contract in whole or in part:

a)   If the supplier/Contractor  fails  to deliver any or all of the goods and to complete any or all works commensurate  with program of completion  within the time period(s) specified in  the contract or  any extension thereof  granted by the purchaser.

b)	If   the   supplier/Contractor fails to perform any other obligation(s) under the contract.

c)  If the supplier/Contractor, in the judgment of the purchaser has engaged in corrupt or  fraudulent practices in competing for or in executing the contract.

30.2	Termination of contract:

If it is found that progress of works are not commensurate with the program of completion as per mutually agreed PERT chart or if the contractor does not fulfill his obligations as per the terms of the specification of APTRANSCO will be entitled to terminate the contract in part or full by giving 15 days notice and get the balance works completed through other agencies at the contractor’s cost and risk.

Warning letters will be issued by Superintending Engineer/400kV or/and Chief Engineer /Construction/400kV if the progress is not satisfactory. If the progress continues to be poor even after the second warning letter, show cause notice/final notice will be issued by the                      Chief Engineer/Construction/400kV. If no satisfactory reply is received or the progress of the works are not improved within 15 days of issue of the final notice/show cause notice, the Chief Engineer/ Construction/400kV shall terminate the agreement, which will be followed by stoppage of all payments to the contractor, encashment of the BGs, and after termination of contract the balance works/supplies shall be completed through alternate agencies at contractor’s risk and cost. The contractor so penalized shall be blacklisted for 3 years from the date of termination of contract.

30.3   In the event of termination of contract in whole or in part due to delay attributable to the contractor, APTRANSCO is entitled to get back equipment/material from the contractor for the payment already made but the material is not put to use, and then get the works done by other agency/agencies for completion of contract by using the said recovered material. The contractor shall have no objection in this regard.

However, the Supplier /Contractor shall continue performance of the Contract to the extent not terminated.

31.0     TERMINATION FOR INSOLVENCY

The Purchaser may at any time, terminate the contract by giving written notice to the Supplier/ contractor without compensation to the supplier/contractor, if the supplier/ contractor becomes bankrupt or otherwise insolvent, provided that such termination will not prejudice or affect any right of action or remedy which has accrued or will accrue thereafter to the Purchaser.

32.0    APPLICABLE LAW

The contract shall be interpreted in accordance with the laws of India

33.0     RESOLUTION OF DISPUTES

All and any disputes or differences arising out of or touching the order based on this specification shall be decided by a panel of arbitrators as detailed below: -

|  | Value of Claim | Panel of Arbitrators |
| --- | --- | --- |
| (i) | Disputes involving amounts up to Rs. 10,000/- and below | Superintending Engineer of APTRANSCO other than the circle to which the disputes relate |
| (ii) | Disputes involving amounts ranging from Rs. 10,001/- to Rs. 50,000/- | Any Chief Engineer of APTRANSCO |

### There shall not be any reference of disputes, the value of which is above Rs.50,000/-to arbitration.  The parties shall approach the competent Civil courts situated in Hyderabad/ Secunderabad twin cities only, if any such disputes shall arise involving more than Rs.50,000/-.

### A reference for adjudication under this clause shall be made by either party to the contract, within one year from the date of intimating the contractor of preparation of final bill or his having accepted the payment.

34.0     JURISDICTION

All and any disputes or differences arising out of or touching the contract will be decided by the courts or tribunals situated in purchasers headquarters only.  No suite or other legal proceedings will be instituted elsewhere.

35.0    DETAILS OF ENCLOSURES:

The following are the attachments enclosed to this order, which form part of the contract.

1. 	Schedules-II   : Prices for erection (Pages - 9)

2.	Annexure  : Prices Variation Clauses for Works (Pages - 2)

Please note that all other terms & conditions of Volume - I of specification will form part of this Order.

Yours faithfully,

Sd/-

CHIEF ENGINEER.

CONSTRUCTION / 400kV,

(For and on behalf of APTRANSCO)

Copy shall be returned to APTRANSCO by Contractor duly signed every page of this order in acknowledgement and acceptance of this order.

We accept the terms and conditions of this order.

SIGNATURE OF THE CONTRACTOR.

CC to: .

Chief Engineer/Civil/APTRANSCO/Vidyut Soudha/ Hyderabad.

Chief Engineer/Telecom/APTRANSCO/Vidyut Soudha/ Hyderabad.

Executive Director( Finance)/APTRANSCO/Vidyut Soudha/Hyderabad.

FA&CCA (CF)/APTRANSCO/Vidyut Soudha/Hyderabad.

Copy to :

P.S to Director (Projects)/APTRANSCO/Vidyut Soudha/ Hyderabad

Superintending Engineer/400kV/Field/APTRANSCO/ Vijayawada.

The Executive Engineer / 400 kV/ Wind Evacuation/ APTRANSCO / Ananthapur

SAO/P&A/APTRANSCO/Vidyut Soudha/Hyderabad.

ANNEXURE

PRICE VARIATION (PV)   for Erection

i)	Price variation shall be applicable for both upward and downward variation in prices of respective items if the delivery of goods / work completion is within the stipulated period mentioned in the purchase order.

ii)	Wholesale Price Index, released from Ministry of Commerce & Industry, Govt. of India will be considered for the items cement, reinforcement steel.

iii)	The completion schedule enclosed to the specification in the form of bar chart shall be the basis for timing of the each activity for calculating the Price Variation during a month. If the schedule is not complied by the Contractor as per the above programme due to the reasons like right-of-way, the particular activity or task can be rescheduled by moving upward or downward on the time axis of the bar chart within the agreement period, as agreed by the Concerned Executive Engineer (Field Officer), as per the actual site conditions. In such cases, the concerned Executive Engineer will record the reasons for re-scheduling/delay of the work.

iv)	Price adjustment shall be calculated separately for reinforcement steel & cement components in proportion to the cost of work done involving the above materials during the billing period as given in the formula given below. The percentage of reinforcement steel & cement components is based on estimated rate only. The price variation amount so obtained will be added to the cost of work done calculated on quoted rate, put up for billing.

v)	The concerned Field Executive Engineer will calculate the Price Variation for the billing period, preferably monthly. For this purpose the contractor shall submit invoice supported by calculation as per formula specified along with documentary evidence for different indices applicable for Price Adjustment.

vi)	Price variation will be limited to the amount arrived based on schedule date of completion or actual date of completion which ever is earlier. Lower of the two indices values will be considered.

vii)	In specific cases like right-of-way problems, for which the contractor is not responsible, extension of the agreement period may be given duly rescheduling the programme of completion with the approval of competent authority. In all such cases, APTRANSCO will consider application of Price variation clause case to case.

Applicable formula for calculating Price Variation for Re-inforcement steel, Cement:

The Price Variation applicable in respect of steel and cement utilized in civil works shall be as per G.O.Ms.No.94, Dt: 16-04-2008 and T.O.O CE (Civil) Ms.No.24,  Dt: 23-04-2008 & T.O.O CE (Civil) Ms.No.84,  Dt: 12.06.2012 of APTRANSCO subject to the following conditions:

a)	The price adjustment shall be applicable within original contract period or period extended on grounds of the departmental delays and valid reasons and shall not applicable to the extension granted on account of the Contractors fault.

b)	The price adjustment shall be applicable for actual components of items of works actually carried out during the period of bill and is allowed for steel and cement utilized in civil works, considering the absolute variation between the estimated rate and the rate approved by the Govt. based on the recommendation of Board of Chief Engineers for the month. The base rate for Reinforcement Steel is Rs.44,000 per MT and for Cement Rs.4100 per MT for the month of March’2013.

c)	i) The price adjustment will be applied where the variation in rates only to the extent where it is above 5% over the estimated rates. Thus if the price excess is 10%, payment will be made only to the extent of 5% (10% - 5%). Further, the same procedure should be also followed for Negative Price variation.

ii) For the time extension period due to

a) delay on account department , price variation (Both +ve and –ve ) is                                    applicable.

b) delay on account of contractor, only negative price variation is applicable.

Necessary supplemental proposal regarding differential rate payable or difference rate recoverable on agreement rates of steel and cement utilized in civil works and structural steel due to price adjustment is to be submitted to the agreement concluding authority for approval.

CHIEF ENGINEER.

CONSTRUCTION / 400kV