TRANSMISSION CORPORATION OF ANDHRA PRADESH LIMITED

VIDYUT SOUDHA ::  HYDERABAD

APTRANSCO- Purchase Manual – Variation on Taxes and Duties – Amendment Issued – Regarding

-------------------------------------------------------------------------------------------------------------------

T.O.O. (CE – Construction-II) Ms.No.12                                                           Dated. 13.11.2013.

READ THE FOLLOWING:

Ref:   	1  T.O.O. (C.E/Construction-400 kV) Ms. No.1 Dt. 03.04.2010.

2. T.O.O. (C.E/Construction) Ms. No. 236 Dt. 12.01.2010

***

Purchase manual at clause 5.19 is stating that any variation in statutory levy or new levies introduced after signing the contract and during the delivery period will be to the account of APTRANSCO. Thus, variation in statutory levies is not considered to the account of APTRANSCO during the period of after bidding and before awarding the contract.

2. The contractors have represented that the Excise duty & VAT were hiked after their bid submission and due to which deduction of excess %age of taxes from their running bills becoming burden on them.  Contractors requested APTRANSCO to take over such burden due to variation in Statutory Levies as same were not in their control.

PROCEEDINGS:

3. APTRANSCO examined the contractors’ above request in detail.

4.  In view of the above, APTRANSCO decided to amend the Purchase Manual in the above subject and decided to consider the taxes as on the date of Tender Calling date as reference and any variation after the Tender calling date will be accounted to APTRANSCO.

5.  Accordingly the clause 5.19 of Purchase Manual for ‘Variation in Statutory Levies’ read with T.O.O. (C.E/Construction-400 kV) Ms. No.1 dated 03.04.2010 is amended as follows:

| Clause NO. | Existing Clause | Amended As |
| --- | --- | --- |
| Statutory Variation: Clause no. 5.19, page 49 of Purchase Manual read with T.O.O. (C.E/Constn-400 kV) Ms. No.1 dtd 03.04.2010. | Any variation up or down in statutory levy or new levies introduced after signing of the contract under this specification will be to the account of Purchaser. Any variation up or down in taxes and duties, or new levies introduced subsequent to bid opening and before award will be considered for comparison purposes. Any increase in statutory levies during the delivery period will be granted with the approval of concerned Chief Engineer and FA&CCA on production of documentary evidence of such increase by the supplier. In case of sub-vendor items Taxes & duties are inclusive in tender price. No statutory variation is applicable. Further price variations in respect of sub-vendor items will be considered on tender prices. This is allowed only once during delivery period i.e., at the time of delivery of goods at factory. | Any variation up or down in statutory levy or new levies introduced after Tender Calling Date will be to the account of APTRANSCO. Any increase in statutory levies will be granted with the approval of concerned Chief Engineer on production of documentary evidence of such increase by the supplier. In case of sub-vendor items Taxes & duties are inclusive in tender price. No statutory variation is applicable. Further price variations in respect of sub-vendor items will be considered on tender prices. This is allowed only once during delivery period i.e., at the time of delivery of goods at factory. |

6.  In view of changes to the Purchase Manual, the corresponding terms & conditions in tender specification are modified as follows:

| Cl.16 at page 152 of specification read with T.O.O. (C.E/Construction) Ms. No. 236 Dt. 12.01.2010 | Any variation up or down in statutory levy or new levies introduced after ‘signing of the contract’ under this specification will be to the account of APTRANSCO. In cases where delivery schedule is not adhered to by the supplier and there are upwards variation / revision after the agreed delivered date the supplier will bear the impact of such levies and if there is downward variation / revision the APTRANSCO will be given credit to that extent. For variation beyond scheduled completion period the payment of taxes shall be limited to the tax rates applicable within the scheduled completion period. a) In cases where the bidder assumes less tax rates and become lowest, upward variation will not be considered. b) In case of bought out items for which the prices are quoted all inclusive of taxes, statutory variation shall not be applicable. | Any variation up or down in statutory levy or new levies introduced after ‘Tender Calling Date’ under this specification will be to the account of APTRANSCO. In cases where delivery schedule is not adhered to by the supplier and there are upwards variation / revision after the agreed delivered date the supplier will bear the impact of such levies and if there is downward variation / revision the APTRANSCO will be given credit to that extent. For variation beyond scheduled completion period the payment of taxes shall be limited to the tax rates applicable within the scheduled completion period. In case of bought out items for which the prices are quoted all inclusive of taxes, statutory variation shall not be applicable. |
| --- | --- | --- |
| Bid Prices: Clause 13.3 page no. 150 of Draft Specification. | It is the responsibility of the bidder to inform himself of the correct rates of the duties and taxes leviable on the materials at the time of bidding. | It is the responsibility of the bidder to know the prevailing statutory taxes. APTRANSCO considers evaluation of bid price on the basis of prevailing tax rates as on the date of ‘Tender Calling Date’. |

7)   These amendments will come into effect from the date of issue of this order.

(BY ORDER AND IN THE NAME OF TRANSMISSION CORPORATION OF ANDHRA PRADESH LIMITED)

Sd/-

DIRECTOR (Projects)

To

The Chief Engineer/Construction-2/VS/ Hyderabad.

The Chief Engineer/Construction-1/VS/ Hyderabad.

The Chief Engineer/LIS/VS/ Hyderabad.

The Chief Engineer/Construction 400 kV/VS/ Hyderabad.

The Chief Engineer/Transmission/VS/ Hyderabad.

The Chief Engineer/Civil//VS/ Hyderabad.

The Chief Engineer/Zone/Metro, Hyd.

The Chief Engineer/Zone, Rural/ Hyderabad

The Chief Engineer/Zone/Kadapa

The Chief Engineer/Zone/Vijayawada

The Chief Engineer/Zone/Visakhapatnam

The Chief Engineer/Zone/Warangal

PS  to Chairperson Managing Director/APTransco/VS/Hyd.

PS  to Joint Managing Director/ HRD, Comml. IPC, & IT/APTransco/VS/Hyderabad.

PS  to Joint Managing Director/ V&S/ APTransco/VS/Hyderabad.

PS to Director /Projects/ APTransco/VS/Hyderabad.

ADE/Tech to Director /Grid, Transmission& Management/ APTransco/VS/Hyderabad.

PS to Director /Finance & Revenue/ APTransco/VS/Hyderabad.

The ED /Finance /APTransco/VS/Hyderabad.

ADE/Tech to Chief Engineer/Construction-2/APTransco/VS/Hyderabad