TRANSMISSION CORPORATION OF TELANGANA LIMITED

| # From: | To: |
| --- | --- |
| # Chief Engineer, | # M/s. Larsen & Toubro Limited, |
| # 400kV, | # Power Transmission & Distribution, |
| # TSTRANSCO, | # Mount Poonamallee Road, Manapakkam, |
| # Vidyut Soudha, | # P.B.No. 979, Chennai – 600089, India, |
| # Hyderabad – 500 082. | # Ph:- +91-44-22704000, 22705000, |
| # Fax. No. 040 – 2332 3933. | # Fax:- +91-44-22705482 (www.Lntecc.com). |

P.O.No.132/OC-06/CE/400kV/SE-I/D1-A4/e-EHVT-06/2017/L&T

D.No.238/2018, Dt:28.05.2018.

Sir,

Sub:	TSTRANSCO - Bid No. e-EHVT-06/2017 – Design, Engineering, Manufacturing, Testing before dispatch, loading, supply and unloading for destination including transportation, insurance and storage for the material/equipment for 400kV Quad Moose DC Line from 400kV Dichpally SS to 400kV Nirmal  SS of length  60kM (approx.)  on Turnkey Basis – Detailed Erection Purchase Order – Issued – Reg.

Ref:	1.	Bid no. e-EHVT-06/2017.

2.	Your offer dt: 22.02.2018 against Bid no. e-EHVT-06/2017.

3.	L.O.I.No. CE/ 400kV/SE-I/D1-A4/ e-EHVT-06/2017/L&T/

D.No.47/ 2018, Dt: 18-04-2018.

4.	Ltr.No.LTC/PTD/TSTRANSCO/2017-18/58/PRN/1495,                                          Dt: 24.04.2018. (Acceptance of L.O.I)

<<<>>>

I, acting for and on behalf of and by the order and direction of the TRANSMISSION CORPORATION OF TELANGANA LIMITED (here in after called ‘TSTRANSCO’) accept the offer of M/s. Larsen & Toubro Limited, (here in after called ‘Contractor’) cited at reference (2) cited read along with their letter under reference (4) cited and TSTRANSCO’s bidding documents for Bid No. e-EHVT-06/2017 for Design, Engineering, Civil & Construction works, Erection, Testing & Commissioning of 400kV Quad Moose DC Line from 400kV Dichpally SS to 400kV Nirmal  SS of length  60kM (approx.)  on Turnkey Basis for a total amount  Rs. 38,37,80,810/- (Rupees Thirty Eight Crores Thirty Seven Lakhs Eighty Thousand Eight Hundred Ten Only) including all taxes and levies as detailed in Schedule – II enclosed, subject to the terms and conditions set out in this order.

This order is  issued in regularization of Letter of Intent (LOI) issued in the reference (3) above and your acceptance of the same under reference (4) cited.

- SCOPE:

The Scope of this order covers Supply, Erection, Testing and Commissioning of 400kV Quad Moose DC Line from 400kV Dichpally SS to 400kV Nirmal  SS of length  60kM (approx.) on Turnkey Basis as detailed below:

- Design of specific towers/extensions/strengthening if required in the project at no additional cost including detailing, proto testing, furnishing of Bill of Material  (BOMs) drawing etc. All the relevant drawings in AUTO CAD to the scale with reproducible tracings in such cases shall also be supplied to the purchaser by the successful bidder at free of cost.

- The new tower/ extensions if any, including detailing, proto testing, furnishing of Bill of Material (BOMs) drawing etc shall be developed and got approved by CPRI, Bangalore.

- Detailed survey (if and where required), check survey, Soil Investigation, laying of Pile/Conventional foundations, river crossing works, developing stringing charts, erection, testing and commissioning of the 400kV DC transmission line employing Quad Moose bundled ACSR Conductor per phase and 1 No.7/3.66 mm GSS earth wire and 1 No. OPGW.

- Cutting & removing of all kinds of trees of all girths & all sizes and also clearing of scrub jungle including transportation and disposal along the route of the line for a total corridor of 52 mtrs.

Also the contract is on TURNKEY basis and hence any other items not specifically mentioned in the specification but which are required for erection, testing & commissioning and satisfactory operation of this line are deemed to be included in the scope of the contract and same shall be arranged by the contractor unconditionally.

The rates indicated in Schedule- II appended to this order are for Erection works.

- ABSTRACT of Schedule:

|  |  | Tender Percentage: -6.31% |  |
| --- | --- | --- | --- |
| Sl.No. | Item Description |  | Amount (in Rs.) |
| 1 | Schedule of Prices for Civil, Construction, Erection, Testing and Commissioning Works (Schedule- II) |  | Rs. 38,37,80,810.00 |
| (Rupees Thirty Eight Crores Thirty Seven Lakhs Eighty Thousand Eight Hundred Ten Only) |  |  |  |

The bids for the subject work were opened on on 24.02.2018

3.0       PRICES AND PRICE ADJUSTMENTS:

3.1     The accepted rates for the items except for cement & reinforcement steel, shall be firm on all accounts such as (i) increase in quantum of work provided in the contract,                          (ii) execution of contract beyond the scheduled completion period for whatever reasons,

(iii) Increase in the rates of material and labour both during and beyond the completion period etc., these prices shall include all the taxes and duties wherever applicable.            Price variation is applicable for items cement, reinforcement steel as per Price Variation clause mentioned at Annexure.

## 3.2       The quantities stated in price schedule are approximate only and unit price shall apply to actual quantities measured on the completed work in accordance with specification and drawings.

Any other items not specifically mentioned in the bidding documents / drawings  but which are required for Erection, Testing and Commissioning of 400kV Quad Moose DC line  are deemed to have been included in the scope of the contract as mentioned in tender specification. The above prices include insurance to be covered by the contractor for the works, workmen’s compensation, and all other insurances required as per tender specification.

3.3	The tender price quoted by the Contractor is 6.31% Less over the ECV of  TSTRANSCO.

4.0	TAXES AND DUTIES:

4.1	The erection prices are inclusive of all taxes like Corpus fund @0.1% on Civil Portion  & GST @ 18% on total Erection value.

4.2	The Contractor will be entirely responsible for payment of taxes and duties, other local taxes or levies if any, license fee, etc., which are to be borne by the company/contractor until the completion of the contract.

4.3	No claim against the variation in taxes and duties or new levies in respect of the transaction between the Contractor and their vendors / sub-suppliers while procuring any components,                 sub-assemblies, raw materials and equipment will be entertained by the TSTRANSCO.

4.4	TSTRANSCO shall not bear any tax liability i.e., Income Tax, surcharge on Income Tax and any other Corporate Tax, irrespective of the mode of contracting. The contractor shall be liable and responsible for payment of taxes, under the provision of the law.  TSTRANSCO as per the respective acts will make deduction towards Income Tax, GST, Labour cess and Corpus Fund at source.

TSTRANSCO is registered under GST Act and Provisional ID is 36AAFC0166J1Z9            CIN No.U40102TG2014SGC094248.

4.5      PAYMENT OF TAXES, LEVIES, DUTIES, STATUTES:

4.5.1   Contractor shall be entirely responsible for payment of all taxes, levies, duties, other local taxes, license fees, etc.

4.5.2    The contractor shall pay all types of fees, levies, taxes, duties etc. required to be paid by any National or State statute, ordinance or other law or any regulation or bye-law of any local or other duly constituted authority in relation to the execution of works and by the rules and regulations of all Public bodies and companies whose property or rights are affected in any way during the execution of works. In compliance to the above, the contractor shall keep the TSTRANSCO indemnified against all such penalties and liability of every kind for breach of any statute, ordinance or law, regulation or byelaw.

4.5.3  	Nothing in the contract shall relieve the contractor from his responsibility to pay any tax that may be levied by the Government on the turnover / profits made by him in respect of the contract.

4.6	TAX AND CESS DEDUCTABLE AT SOURCE:

4.6.1	As per provision of Income tax Act, applicable Income tax, GST and Labour cess and corpus fund will be deducted at source at all stages of payment of the bills and same will be remitted to the concerned department as per the rules / acts of the State / Central Government.

The GST will be deducted in accordance with the orders issued by Government of India/Telangana from time to time at the rates, as applicable under TDS at all stages of payment of the bills and same will be remitted to the concerned department as per the rules / acts of the State / Central Government.

4.7   	SEINORAGE CHARGES:

Seignorage charges shall be paid to the Assistant Director Mines & Geology Department as per existing rules in vogue.

4.8		STATUTORY VARIATION:

Any variation increase or decrease in statutory levy or new levies introduced after Tender calling date will be to the account of TSTRANSCO.

Any variation increase or decrease in taxes and duties, or new levies introduced subsequent to bid closing and before contract award shall be regulated in the contract agreement by the agreement concluding authority.

Any increase in statutory levies will be granted with the approval of concerned                          Chief Engineer on production of documentary evidence provided the variation is within the scheduled completion period of contract. This is allowed only once during delivery period i.e. at the time of delivery of goods at factory.

In cases where the Contractor does not adhere to schedule of programme of works and if there is any upward variation/revision in taxes & duties after the agreed schedule of programme of works, the Contractor shall bear such impact of levies and if there is any downward variation/revision, the credit shall be passed on to TSTRANSCO to that extent irrespective of scheduled completion of period of contract.

5.0		DELIVERY / COMPLETION PERIOD:

Erection works shall commence in third week of third (3rd) month from date of handing over of detailed survey profiles and complete (in full shape) the Erection, Testing & Commissioning within Fifteen (15) months from the date of handing over of detailed survey profiles.

6.0	TERMS OF PAYMENT FOR ERECTION:

6.1	The payment will be made through PFC.

Payments for the erection will be made up to 90 % of the monthly bills at the rates approved in the schedules for the items of work done.  For this purpose the Contractor shall submit monthly bills to the Executive Engineer regularly to ensure payments in time. The Contractor shall give full details of items of works done against each location in support of the bill.  Bills submitted without supporting details will not be taken into cognizance.

Out of the balance 10% amount, 5% payment will be released after completion of all works & upon submission of material account, provided if all the works including testing & commissioning of the line are completed and the same is certified by the purchaser.

The balance final 5% will be paid after completion of one year performance guarantee period reckoned from the date of completion of all the works as per contract or after all the balance materials leftover after completion of works are handed over to the TSTRANSCO, which ever is later. The date of commissioning/energizing the line will not be considered for reckoning the purchase guarantee period.

6.2	The Bank Account RTGS details furnished by the company are as follows:

Name of Bank	:	Citi Bank

Bank Branch	: 	Greater Bombay, Mumbai.

A/C Number	       :  	15963107

A/c Name	       :  	M/s. Larsen & Toubro Limited,

Bank Address       :  		Bombay Mutual building, 293,Dr D N Road, Fort,

Mumbai-400001

IFSC Code	:	CITI0100000

6.3    	In case, the balance materials are returned to TSTRANSCO well before the completion of the performance guarantee period, the 5% amount will be released against an additional bank guarantee for equal amount, which shall be valid for the performance guarantee period and also provide six months claim period. “All banking charges should be to the account of the Contractor”.

The payments are subject to submission of Performance Security with validity of Twelve (12) months with a further claim period of two months as on date of check measurement of materials and works.

7.0    	FINAL PAYMENT:

Whenever, in the opinion of owner, the work covered by the Contract has been completed, he shall prepare a final abstract showing the total amount of work done by Contractor and its value under and according to the terms of the Contract.  From the total value thus arrived at shall be deducted all previous payments and all deductions made in accordance with the provisions of the Contract.  The remainder shall be paid by owner to Contractor within three months after the date of owner’s final certificates.

7.1      Where the Vendor/Contractor requests for the payment in advance before the “scheduled date of payment” would be examined by the negotiations committee to decide whether such facility could be extended or not and if found acceptable the Contractor should agree to offer a rebate/ discount @ 0.3% per week or part there of for the advancement.  Based on the decision, the Finance & Accounts wing will release priority payment to such Contractor after availing of the rebate/ discount.

7.2	The payment for super-structure erection shall be based on the calculated weights of tower and their extensions as per the approved bill of material for each type of tower.

7.3      The payment for excavation and concreting shall be based on the approved design volumes of excavation and concreting.

7.4 	No claim for idle period resulting from any "Force Majeure" condition shall be   entertained by the purchaser.

- PERFORMANCE SECURITY:

8.1       i.	It is noted that M/s. Larsen & Toubro Limited, have furnished the following                5% Bank Guarantee towards Performance Security (Erection) as per Clause 39, Section - III ITB as per the LOI issued vide reference (3) cited as under:

| Sl.No | Name of the Bank | Bank Guarantee No. & Date | Amount in Rs. | Validity Period/ Claim Period | Towards |
| --- | --- | --- | --- | --- | --- |
| 1 | State Bank of India, Chennai | B.G.No.0999918BG0000343 Dt:27.04.2018 | 1,91,89,050/- | 31.08.2020 / 31.10.2020 | Performance Security- (5% Value of Erection Portion) |

- The contractor has to furnish the requisite amendment for 5% value of Erection portion and extend the validity of Bank Guarantee as and when requested by TSTRANSCO as per the provision of the contract.

- The Purchaser will discharge the above bank guarantees  after completion of the warranty/ Guarantee period as per the provisions of contract.

8.2	The Bank guarantee for Performance Security should be extended suitably in case the equipment / material is found defective and not attended to within the performance guarantee period or any other contractual obligations are not fulfilled.

8.3	    The purchaser will discharge the Performance Security after completion of the contract 		and within 60 days of the expiry of the warranty.

9.0		INDEMNITY BOND FOR ALL MATERIALS:

For all materials supplied by the Contractor and through the sub-vendors, the Contractor shall take delivery of materials after executing an indemnity bond in favour of the Purchaser against loss, damage and any risks involved, for the full value of the materials.  This indemnity bond shall be valid till the scheduled date of testing, commissioning and handing over of the line to the Purchaser.

10.0   	CONTRACT AGREEMENT:

10.1  	The Contractor shall enter into a Contract Agreement in the prescribed proforma as indicated in Annexure-X of Volume-I of bidding documents with the Purchaser within thirty (30) days from the date of “Notice  of  Award of Contract" or within such extended time as may  be  granted  by the Purchaser.

10.2  	The agreement shall be executed at the Office of the Chief Engineer/400kV, TSTRANSCO, Vidyut Soudha, Hyderabad on a date and time to be mutually agreed.

The expenses for the preparation and stamping the contract agreement shall be to the account of the Contractor.

11.0 	WARRANTY/GUARANTEE:

ERECTION:

Twelve (12) calendar months from the date of completion of the contract, unless otherwise agreed in writing by Purchaser, will be deemed to be the 'Defect Liability Period'.  The works shall not be considered as completed until Owner has certified in writing that they have been virtually completed and the defects liability period shall commence from the date of such certificate.  In case any defects in the work due to bad materials, and/or bad workmanship develop in the work before the expiry of the period, the contractor, on notification by Purchaser shall rectify or remedy the defects at his own cost and he shall make his own arrangements to provide materials, labour, equipment and any other appliances required in this regard. The performance security will be returned to contractor only after the expiry of this defect liability period.  In case even on due notification by purchaser, the contractor fails to rectify or remedy the defects, purchaser shall have the right to get this done by the other agents and recover the cost incurred by deductions from the retention amount due to the contractor, in case this cost is within the value of the performance security, and if not, contractor shall be liable to pay to purchaser the balance amount.

The provisions of this clause shall apply to all replacements or renewals carried out by the contractor as if the replacements or renewals had been taken over on the date they were completed.

The Defects Liability period for the works shall be extended by a period equal to the period during which the works cannot be used by reason of a defect or damage. If only part of the works is affected the Defects Liability period shall be extended for that part.  In neither case Shall the Defects Liability period be extended by more than one year.

12.0 	FORCE MAJEURE:

12.1	Force majeure is herein defined as

- Any cause which is beyond the control of contractor or Purchaser, as the case may be.

- Natural phenomenon including but not limited to weather conditions, floods, drought, earthquakes and epidemics.

- Acts of any governmental authority, domestic or foreign, including but not limited to war, declared or undeclared, priorities, quarantine, embargoes, licensing control or production or distribution restrictions.

- Accidents and disruptions including but not limited to fires, explosions, breakdowns of essential machinery or equipment and power shortages.

- Transportation delay due to force majeure or accidents.

- Strikes, slowdown, lockouts and sabotage.

- Riots and civil commotions.

  - If a Force Majeure situation arises, the supplier/contractor shall promptly notify the Purchaser within 10 days in writing of such condition and the cause thereof.  Unless otherwise directed by the Purchaser in writing, the supplier/contractor shall continue to perform its obligations under the contract as far as is reasonably practical, and shall seek all reasonable alternative means for performance not prevented by the Force Majeure event.

  - The Contractor or the purchaser shall not be liable for delays in performing his obligations resulting from any force majeure cause as referred to and/or defined above.

  - Notwithstanding the provisions of clauses 12.1, 12.2, 12.3, the supplier/contractor shall not be liable for forfeiture of its performance security, penalty for late delivery or termination for default, if and to the extent that, its delay in performance or other failure to perform its obligations under the contract is the result of an event of Force Majeure.

  - No price variance is allowed during the period of Force Majeure Conditions.

13.0	PENALTY FOR ERECTION:

13.1	The time stipulated in the contract for the execution and completion of the works shall be deemed to be the essence of the contract. In the event the contractor fails to execute, complete and deliver the works within the time specified in the contract, then the contractor shall pay to Purchaser as and by way of penalty an amount equal to Half percent (1/2%) of the value of the unperformed services for each week's delay beyond the date of completion specified in the contract. However, such payments shall not exceed 10% of the total value of the contract. Purchaser may, without prejudice to any method of recovery, deduct the amount for such damages from any amount due or which may become due to the contractor. In the event of extension of time being granted by Purchaser in writing for completion of the work, stated in Clause No.6.0 of GCE, Volume-I of the specification, this penalty clause will be applicable after the expiry of such extension period.

In case of non-achievement of Targets of the scheduled works by the Contractors when compared with the PERT charts as accepted in the Kickoff meetings, whatever may be the reasons, the TSTRANSCO shall levy and collect the penalty @ 1% per month of value of non-achieved targets fixed in the Kickoff meeting. However if the work is completed within the total scheduled completion period the penalty recovered so i.e penalty recovered towards non-achievement of Targets by the Contractors when compared with the PERT charts as accepted in the Kickoff meetings shall be released.

Penalty shall be calculated while admitting the final bill, duly taking into account, extension of completion period if any, and the penalty shall be recovered along with applicable GST.

However to ensure availability of sufficient amount for deducting penalty a recovery of 0.5% of the value of supply/work, delayed, per week(or part thereof, as the case may be) shall be adjusted against the Penalty (+GST) levied while admitting the final bill.

  - PENALTY FOR DEFICIENCY IN QUALITY OF WORKS:

It has been observed that while executing the EHT line/ Sub-station works, certain lapses or omissions are being committed by the contractors, which have an effect on the stability of the line or structure.  To prevent such lapses on the part of the contractors and bring about greater awareness on their part it is proposed to levy a penalty on the defaulting contractors.

The following instructions are therefore issued in this regard for strict adherence by officers to ensure Quality of works in execution of transmission lines and Substations in the field.  In case any deficiency in quality of works is found during the course of execution of works and any category wise deficiency in quality of works, TSTRANSCO will impose penalty and take other actions as indicated below:

| S. No. | Deficiency in quality from the specification/ Agreement such as |  |  | Instance wise Minimum penalty leviable in Rupees during the same work by the contractor |  |  |  |  |  | Duration of disqualification of the contractor for participation in the tenders of TSTRANSCO in the event of further instance. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1st Instance |  | 2nd Instance |  | 3rd Instance |  |  |  |
| Category-I | Not using (i) prescribed shoring, shuttering and dewatering equipment (ii) measurement boxes, (iii) form boxes for steel measuring boxes, (iv) not providing adequate number of chairs to the steel reinforcements, (v) not carrying out back filling and compaction of the foundation pits in layers and leveling the tower footings properly, (vi) not ensuring that the excavated earth is dumped at least 2 meters away from the pit etc., (vii) not providing coping to tower leg/stubs and (viii) not providing water tanker, Earth rammers/ Earth vibrators. |  |  | 5000 |  | 10000 |  | 15000 |  | Debarred from participating in future tenders for a minimum period of one year |  |
| Category-II | Use of reinforcement steel without ISI marking, not using vibrators for effective consolidation of the concrete during foundation works, not using proper templates for firmly keeping the stubs in position when templates are supplied by the contractor and improper fixing of stubs, non ensuring of tower verticality, use of rusted stubs and tower parts if supply is by the contractor, non painting of butt joints and rusted stubs with zinc rich paint immediately after erection of the towers and stringing, non fixing of earth flat to the stub, non deployment of technical personnel for supervision of works by the contractor. |  | 7500 |  |  | 15000 |  | 22500 |  | Debarred from participating in future tenders for a minimum period of one year. |  |
| Category-III | Use of improper grade/quality of raw material like HBG metal, water and sand for concreting using clogged and/or lump/ clotted cement for concreting not ensuring proper curing for foundation concrete, not ensuring that all the members of the tower are placed in position and firmly fixed with bolts and nuts immediately after erection of tower. | 10000 |  |  | 20000 |  | 30000 |  | Debarred from participating in future tenders for a minimum period of one year. |  |  |

14.0  	Incentives for early completion of the works:

The contractors who completes the transmission line works well before the scheduled completion period will be awarded incentives as per the formula given below:

Incentive Bonus Formula.

I = Z * {Y/(X/3)} * 4%,

Where,

I   =       Incentive Bonus,

Z   =      Project cost

Y   =     Days equivalent to the difference of the Scheduled Project commissioning

date and the actual Project commissioning date.

X =       Time period in days for completion of a Project specified in the

Specification / bidding documents of the Project.

However Y should be > 30 days and Incentive Bonus is limited to 4% of the Project Cost.

15.0    INSURANCE FOR ERECTION:

15.1	In addition to the conditions covered under the clause entitled ‘Insurance’ in ‘General Conditions of Contract’, the following provisions will apply to the portion of the 'Works' to be done beyond the CONTRACTOR's own or his SUB-CONTRACTOR's works. Comprehensive Insurance of equipment/materials during erection and commissioning, Workmen's Compensation Insurance, Comprehensive Automobile Insurance and Comprehensive General Liability Insurance shall be the responsibility of the CONTRACTOR. The Contractor shall at his own expense arrange to effect and maintain until the completion of the contract, Insurance policies, with an insurance company approved by Purchaser, against all risks in respect of which contractor is required under this clause to indemnify purchaser. In  particular, the Contractor shall effect and maintain an insurance policy of at least Rs.3.00 lakhs for one person and Rs.5.00 lakhs per accidental for injury or death and at least Rs.5.00 lakhs per accident for third party property damage, to indemnify purchaser against all third party accident/damage claims which may arise in respect of the work or in consequence thereof. The Contractor shall also maintain an insurance policy against all claims which may be made upon Purchaser whether under the Workmen's Compensation Act or any other statue in force during the currency of the contract or at common law in respect of any employee of contractor or any sub-contractor. All such insurance policies shall be in the joint names of purchaser and contractor and shall be deposited with purchaser. The Contractor shall be responsible for anything which may be excluded from the insurance policies referred to above and also for all other damage to any property or persons out of and incidental to the negligence or defective carrying out of this contract.

All costs on account of insurance liabilities covered under the contract will be on the contractor's account and will be deemed to have been included in the contract price.

15.2	Workmen's Compensation Insurance:

This insurance shall protect the CONTRACTOR against all claims applicable under the Workmen's Compensation Act, 1948 (Government of India). This policy shall also cover the CONTRACTOR against claims for injury, disability, disease or death of his or his SUB-CONTRACTOR's employees, which for any reason are not covered under the Workmen's Compensation Act, 1948.

The liabilities shall not be less than :

Work Men’s compensation	-	As per statutory provision

Employees liability		- 	As per statutory provision.

  - Comprehensive Automobile Insurance:

This insurance shall be in such a form to protect the CONTRACTOR against all claims for injuries, disability disease and death to members of public including the PURCHASER's men and damage to the property of others arising from the use of motor vehicles during on or off the 'Site' operations, irrespective of the purchaser-ship of such vehicles.

The liability covered shall be as herein indicated:

Fatal injury		:  Rs.  1,00,000 each person

Rs.  2,00,000 each occurrence

Property damage	:  Rs.  1,00,000 each occurrence

  - Comprehensive General Liability Insurance:

This insurance shall protect the CONTRACTOR against all claims arising from injuries, disabilities, diseases or death of members of public or damage to property of others due to any Act or omission on the part of the CONTRACTOR, his agents, his employees, his representatives and SUB-CONTRACTORs from riots, strikes and civil commotion. This insurance shall also cover all the liabilities of the CONTRACTOR arising out of the clause entitled 'Clause. 32.0’ of GCC Indemnify the Purchaser under 'General Conditions of Contract'.

  - The hazards to be covered will pertain to all the works which and areas where, the CONTRACTOR, his SUB-CONTRACTOR, his agents and his employees have to perform work pursuant to the 'Contract'.

  - The above are only illustrative list of insurance covers normally required and it will be the responsibility of the CONTRACTOR to maintain all necessary insurance coverage to the extent both in time and amount to take care of all his liabilities either direct or indirect, in pursuance of the 'Contract'.

15.7   	Fire Insurance:

Unless otherwise instructed by the PURCHASER/ENGINEER, the CONTRACTOR shall, on signing the 'Contract', insure the works and keep them insured until the completion of the 'Contract' against loss or damage by fire, with the Company to be approved by the PURCHASER/ENGINEER, in the joint names of the PURCHASER and the CONTRACTOR for such amount and for any further sum, if called upon to do so by the PURCHASER/ ENGINEER, the premium of such further sum being allowed to the CONTRACTOR as an authorised  extra.  Such policy shall cover the property of the PURCHASER only and shall not cover any property of the CONTRACTOR or any SUB-CONTRACTOR, or his employees.  The CONTRACTOR shall deposit the policy receipts for the premium with the PURCHASER/ENGINEER within twenty one (21) days from the date of signing the 'Contract' unless otherwise instructed by the PURCHASER/ENGINEER.

In default of the CONTRACTOR insuring as provided above, the PURCHASER may so insure and may deduct the premiums paid from any moneys due, or which may become due to the CONTRACTOR.  The CONTRACTOR shall, as soon as the claim under the policy in settled, or the work reinstated by the insurance office should they elect to do so, proceed with all due diligence with the completion of the 'Works' in the same manner as though the fire had not occurred and in all respects under the same conditions of 'Contract'. The Contractor in case of rebuilding or reinstallment after fire, shall be entitled to such extension of time for completion as the Purchaser/Engineer may deem fit.

15.8     Comprehensive transport, storage, erection cum commissioning insurance.

15.9  	All the equipment and materials being supplied by the Contractor shall be kept completely insured by the Contractor at his cost from the time of despatch from the Contractors Works, upto the completion of erection, testing and commissioning at site and taking over the works by the Purchaser in accordance with the contract.

15.10 The Contractor shall inspect all the material received at destination store and furnish a loss/damage report to Purchaser within a week of receipt of material at site, and provide all required assistance to Purchaser in lodging insurance claims thereupon.  In case of loss to Purchaser due to delays in submitting the loss/damages report by the contractor, Purchaser will be within his right to deduct such losses from the contractor's progressive payments. All the equipment and materials being supplied by the Purchaser shall be kept insured by the contractor against loss, damage, theft, pilferage, fire etc., from the point of unloading upto the time of taking over of the works by the purchaser including handling, transportation, storage, erection, testing and commissioning etc., and the contractor shall be fully responsible for making good of any loss or damage at his own cost.  All costs for such insurance shall be to the contractor account and shall be deemed to be included in the contract price.

15.11  It will be the responsibility of the Contractor to lodge, pursue and settle all claims with the Insurance Company in case of any damage, loss, theft, pilferage or fire and the Purchaser shall be kept informed about it.  The losses, if any, will have to be borne by the Contractor, if the claims are not lodged and pursued properly or in time or if the same are not settled by the insurance company. The contractor shall replace the lost/damaged materials (own and the Purchaser's supplied) promptly irrespective of the settlement of the claims by the underwriters and ensure that the work progress is as per agreed schedules. The losses, if any, in such replacement will have to be borne by the contractor.

16.0	SECURITY (WATCH & WARD):

The CONTRACTOR shall have total responsibility for all equipment and materials in his custody stored, loose, semi-assembled and/or erected by him at 'Site'. The CONTRACTOR shall make suitable security arrangements including employment of security  personnel to ensure the protection of all   materials, equipment and 'Works' from theft, fire, pilferage and any other damage and loss.

17.0	VARIATION IN QUANTITIES AND RATES:

For work items covered in Schedule:

a)	For quantities increased up to 50% over and above the Scheduled quantities:  The rates accepted for individual items shall hold good up to 50% over and above the agreement quantities.

b)	For quantities increased beyond 50% over and above the Scheduled quantities:  The rates payable for the quantities beyond 50% over and above the agreement quantities will be TSTRANSCO estimated rate or accepted rate whichever is less.

18.0  PURCHASER’S RIGHT TO VARY THE SCOPE DURING THE PERIOD OF CONTRACT:

Purchaser may change the scope of the Contract based on the priorities and may subsequently extend for balance scope with the prices quoted if required.

Purchaser reserves the right to increase or decrease the scope stated above as per requirement up to (+) or (-) 50% during the execution of the order with the quoted prices.

19.0      QUALITY ASSURANCE PROGRAMME:

The contractor shall submit quality plan for the works to be carried out indicating the procedures and quality control activities and got approved prior to commencement of erection works. However, this shall not relieve the contractor of any of his contractual responsibilities under the contract.

- 20.0      KICK – OFF MEETING:

- The targets fixed in the kick-off meeting signed by both TSTRANSCO and the Contractor shall become a part of the Contract. The targets fixed in the kick-off meeting are final and the progress shall be reviewed periodically.

- The Contractor or his representative shall invariably attend the meeting whenever called. The representative of the Contractor who attends the kick-off meeting and review meetings shall be qualified and shall be authorized by the Contractor with details of qualification, responsibility and designation of the authorized person.

21.0   INCIDENTAL SERVICES:

  - As specified in the relevant bid documents the Supplier/ Contractor may be required to provide any or all of the following services: -

        - Performance or Supervision of on site assembly and / or start up of the supplied material / equipment.

        - Furnishing of tools required for assembly and/or maintenance of the supplied Goods;

        - Furnishing of a detailed operations and maintenance manual for each appropriate unit of the supplied Goods;

        - Performance or supervision or maintenance and/or repair of the supplied Goods, for a period of time agreed upon by the parties, provided that this service shall not relieve the Supplier of any warranty obligations under this Contract; and

(e) 	Training to the Purchaser’s personnel, at the Supplier's plant and/or on site, in assembly, start-up, operation, maintenance and/or repair of the supplied Goods.

21.2  	Prices charged by the Supplier for the above incidental services, should be included in the contract price and any extra changes will not be considered.

22.0  	SUPPLEMENTAL/NEW ITEMS AND PROCEDURE FOR WORKING OUT        	RATES:

The Contractor is bound to execute all supplemental items that are found essential, incidental and inevitable during execution of the contract at the rates to be worked out as below: -

22.1  	SUPPLEMENTAL ITEMS /NEW ITEMS:

i) 	For the items relating to the Schedule-II where the rate can be deduced from the estimate or TSTRANSCO / DISCOMS / common SSR, the rate applicable will be the estimated / SSR rate +/- tender percentage quoted/ accepted by the Contractor for Schedule–II.  The schedule of rates adopted for supplemental items / new items shall be from the current SSR applicable during the execution period.

ii) 	For the items relating to the Schedule where the rates of new items cannot be deduced from the estimate / SSR, the rate payable will be arrived based on the prevailing market rates duly enquiring / collecting quotations and observing the reasonableness of the rates by the Purchaser.

22.2 	The contractor shall plan and procure the materials indicated in the schedule ‘I’ duly verifying with the approved layout and profile so that the procured quantities match with actual requirement to avoid excess supply of materials. The Executive Engineer shall give the details of the materials such as quantities of type wise towers and extensions and other line materials based on the line approved profile and the quantities of type wise structures and other materials based on the approved layout on the date of Kickoff meeting without fail.

22.3  The Schedule time required to complete the new / supplemental items including the balance work will be indicated in the approval letter issued for new / supplemental items.

23.0	PHOTOGRAPHS AND PROGRESS REPORT:

23.1 	Contractor shall furnish three (3) prints to the PURCHASER/ENGINEER of progress photographs of the work done at 'Site'.  Photographs shall be taken when and where indicated by the PURCHASER/ENGINEER or his representative.  Photographs shall be adequate in size and number to indicate various stages of erection.  Each photograph shall contain the date, the name of the CONTRACTOR and the title of the photograph. Normally photographs may be taken once every 15 days and for all special events.

  - The above photographs shall accompany the fortnight/ monthly progress report detailing out the progress achieved on all erection activities as compared to the Schedules. The report shall also indicate the reasons for the variance between the scheduled and actual progress and the action proposed for corrective measures wherever necessary. The contractor shall furnish progress reports as and when requested by the PURCHASER/ ENGINEER.

23.3    Photographs shall be taken by the contractor for each tower location of EHT lines in the  following stages of

- After excavation is over in normal soils.

- Before and after blasting in Hard rock soils.

- During dewatering.

- During concreting.

- Shoring & strutting.

The photographs should be clear. The Contractor shall submit both hard copy and soft copy (2 sets) to the Engineer in charge immediately.

24.0	TREE/CROP COMPENSATION, RIGHT-OF-WAY, CUTTING OF TREES, ETC.

24.1	Payment of compensation for damaged crops or fruit bearing trees shall be initially made by the contractor, which will be reimbursed by TSTRANSCO later on. The compensation so payable in respect of damaged crops shall be based on the assessment of MRO.  In respect of the trees, compensation so payable is the lowest of the rates fixed by the Horticulture/NABARD/MRO. The contractor shall take up the payment of compensation amount only after written approval by the Executive Engineer.  The payment shall be made in the presence of representatives of 400kV, Accounts and Vigilance wings of TSTRANSCO. The Superintending Engineer/400kV/Construction/ Karimnagar shall finalize the compensation claims.

  - The contractor shall take all possible steps to see that standing crops etc. are not damaged during execution of works.  When such damage is inevitable, the compensation will be borne by the TSTRANSCO to the extent of land required for laying of foundation, provided the damage is with prior concurrence of the Executive Engineer. The contractor shall bear the compensation for damages caused without prior concurrence of the Executive Engineer concerned.  Any extra land required by the contractor temporarily for dumping of the construction material and consequent damage to the crops etc. shall be the responsibility of the contractor.

  - In the event of any obstruction being encountered from the local villagers of authorities, the contractor shall immediately notify the Executive Engineer who shall take such steps as may be necessary to clear the obstruction.  The contractor or his representative or gangs shall not adopt antagonistic attitude towards the village authorities with whom they may come into contact, but shall immediately report to the Executive Engineer any case of obstruction which cannot be settled amicably.  No trees shall be cut until the TSTRANSCO has made necessary arrangement with the authorities concerned and permission is given to the contractor to fell such trees.  The TSTRANSCO shall arrange to remove the obstacles as soon as possible.  At times however, it may not be possible for the TSTRANSCO to arrange right-of-way for laying foundations or erecting the towers or stringing the line.  At all such times, the contractor shall shift his gangs to other locations.  The rates quoted shall cover all such contingencies and no extra payments shall be claimed for such contingencies.

24.4 	The TSTRANSCO will arrange the right-of-way along the transmission line route. Any avoidable or deliberate damage done to standing crop or private property by the erection contractor’s labourers shall be the erection contractor’s responsibility.

The erection contractor shall take all reasonable steps for preventing damage to crops during execution of the contract work.

Clearing of obstructions falling in the right-of-way as per IS:5613  (part-2, section-2) –1985 and lopping or trimming of the portion of the trees falling within the minimum electrical clearance zone shall be the responsibility of the contractor. And also, any lopping or trimming of tree branches obstructing the line of sight during check survey shall be the responsibility of the erection contractor.

25.0     SURPLUS MATERIALS:

On completion of the works material account shall be settled and all surplus materials handed over to the contractor for erection shall be returned to the Engineer by and at the expense of the contractor in the Purchaser's store(s) itself.

- The contractor within two (2) months from the date of completion of the line (ready for charging) shall return and account for the surplus materials, if any otherwise the material is deemed to be sold to the contractor at DOUBLE the rate of issue of material and recoveries shall be effected in the contractor’s Bills accordingly.

26.0    CORRESPONDENCE:

All the correspondence regarding the works / payments and other field matters shall be addressed to the Superintending Engineer/400KV/Const./Karimnagar with copies marked to this office.

All the correspondence on all the technical matters shall be addressed to this office with   copies marked to the Superintending Engineer/400KV/Const./Karimnagar.

27.0    GENERAL CONDITIONS OF CONTRACT:

- Except in so far as it is provided otherwise in this contract, all the general, technical,     commercial terms and conditions stipulated in the bidding documents of Volume – I & II for this contract shall be complied with.

28.0	DESIGN AND DRAWINGS:

The structural drawings for towers and their foundations shall be provided by the Purchaser. Wherever the drawings and designs are provided by TSTRANSCO, the suitability of these design and drawings shall be verified by the Contractor for design requirements as per standards, site and soil conditions based on the soil investigation and furnish the detailed design verification calculations before execution if sought by TSTRANSCO. Standard BOMs for towers, stubs will be communicated to the contractor after placement of Purchase Order. Substitutions if any of steel sections of the tower parts with higher size due to non-availability or otherwise, shall be to the contractors account. The purchaser will not accept any liability on this account. The supplier/contractor shall raise the invoices as per standard BOMs. In case of minor variation in BOM approved after proto inspection, only the approved standard BOM will be invoiced and paid.

  - Where design of a particular tower extension / leg extension is not available with the purchaser or where any modification in the design or new design is required, the contractor shall have to design the same to TSTRANSCO at no additional cost, including detailing, proto testing, furnishing of Bill of Material (BOMs) drawing etc.  All the relevant drawings along with reproducible tracings in such cases shall also be supplied to the purchaser by the contractor at free of cost.

  - The scope of work also includes redrawing of existing structural and shop drawings of all the towers being used in the project using AutoCAD duly certifying their correctness and to be handed over to TSTRANSCO in hard and soft copies.

29.0     SUSPENSION, TERMINATION BY PURCHASER FOR CONVENIENCE:

29.1	The Purchaser reserves the right to suspend and re-instate execution of the whole or any part of the 'Works' without invalidating the provisions of the 'Contract'. Orders for suspension or reinstatement of the 'Works' will be issued by the Purchaser or Engineer to the Contractor in writing.  The time for completion of the works will be extended suitably to account for duration of the suspension.

29.2  	Any necessary and demonstrable cost incurred by the Contractor as a result of such suspension of the 'Works' will be compensated by the Purchaser provided such costs are substantiated to the satisfaction of the Purchaser or the Engineer. The Purchaser shall not be responsible for any liabilities if suspension or delay is due to some default on the part of the Contractor or his sub-Contractor or due to force majeure conditions.

  - The Purchaser may, by a written notice sent to the supplier/contractor terminate the contract, in whole or in part, at any time, for its convenience. The notice of termination shall specify that termination is for the Purchaser's convenience, and extent to which performance of work under the Contract is terminated, and the date upon which such termination becomes effective.

  - The goods and services that are complete and ready for despatch shall hand over within 30 days after the supplier's/contractor’s receipt of notice of termination shall be purchased by the Purchaser at the contract terms and prices.  For the remaining goods, the purchaser may select to have any portion completed and delivered at the contract terms and prices.

  - In the event of any dispute in regard to the price of the 'Works' and portion of the payment to be made to the CONTRACTOR, the decision of the Purchaser shall be final.

The CONTRACTOR will be further required to transfer the title and provide the Purchaser   with the following, in the manner and as directed by the Purchaser:

- Any completed 'Works'.

- Such partially completed ‘Works’ including drawings, information’s and contract rights as the CONTRACTOR as specifically performed, produced or acquired for the performance of the 'Contract'.

30.0	TERMINATION FOR DEFAULT:

30.1    	The purchaser may, without prejudice to any other remedy for breach of contract, by written notice of default sent to the supplier/ Contractor, terminate the contract in whole or in part:

a)   	If the supplier/Contractor  fails  to deliver any or all of the goods and to complete any or all works commensurate with program of completion within the time period(s) specified in the contract or any extension thereof granted by the purchaser.

b)	If the supplier/Contractor fails to perform any other obligation(s) under the contract.

c)  	If the supplier/Contractor, in the judgment of the purchaser has engaged in corrupt or fraudulent practices in competing for or in executing the contract.

30.2	Termination of contract:

If it is found that progress of works are not commensurate with the program of completion as per mutually agreed PERT chart or if the contractor does not fulfill his obligations as per the terms of the specification of TSTRANSCO will be entitled to terminate the contract in part or full by giving 15 days notice and get the balance works completed through other agencies at the contractor’s cost and risk.

Warning letters will be issued by Superintending Engineer/400KV/Const/ Karimnagar or/and Chief Engineer/400kV/Vidyut Soudha/Hyderabad if the progress is not satisfactory. If the progress continues to be poor even after the second warning letter, show cause notice/final notice will be issued by the Chief Engineer/ 400kV/Vidyut Soudha/ Hyderabad. If no satisfactory reply is received or the progress of the works are not improved within 15 days of issue of the final notice/show cause notice, the Chief Engineer/ 400kV/Vidyut Soudha/Hyderabad  shall terminate the agreement, which will be followed by stoppage of all payments to the contractor, encashment of the BGs, and after termination of contract the balance works/supplies shall be completed through alternate agencies at contractor’s risk and cost. The contractor so penalized shall be blacklisted for 3 years from the date of termination of contract.

30.3      In the event of termination of contract in whole or in part due to delay attributable to the contractor, TSTRANSCO is entitled to get back equipment/material from the contractor for the payment already made but the material is not put to use, and then get the works done by other agency/agencies for completion of contract by using the said recovered material. The contractor shall have no objection in this regard.

However, the Supplier /Contractor shall continue performance of the Contract to the extent not terminated.

31.0     TERMINATION FOR INSOLVENCY:

The Purchaser may at any time, terminate the contract by giving written notice to the Supplier/ contractor without compensation to the supplier/contractor, if the supplier/ contractor becomes bankrupt or otherwise insolvent, provided that such termination will not prejudice or affect any right of action or remedy which has accrued or will accrue thereafter to the Purchaser.

32.0    APPLICABLE LAW:

The contract shall be interpreted in accordance with the laws of India.

33.0     RESOLUTION OF DISPUTES:

All and any disputes or differences arising out of or touching the order based on this specification shall be decided by a panel of arbitrators as detailed below: -

|  | Value of Claim | Panel of Arbitrators |
| --- | --- | --- |
| (i) | Disputes involving amounts up to Rs. 10,000/- and below | Superintending Engineer of TSTRANSCO other than the circle to which the disputes relate |
| (ii) | Disputes involving amounts ranging from Rs. 10,001/- to Rs. 50,000/- | Any Chief Engineer of TSTRANSCO |

### There shall not be any reference of disputes, the value of which is above Rs.50,000/-to arbitration.  The parties shall approach the competent Civil courts situated in Hyderabad/ Secunderabad twin cities only, if any such disputes shall arise involving more than Rs.50,000/-.

### A reference for adjudication under this clause shall be made by either party to the contract, within one year from the date of intimating the contractor of preparation of final bill or his having accepted the payment.

34.0     JURISDICTION:

All and any disputes or differences arising out of or touching the contract will be decided by the courts or tribunals situated in purchasers headquarters only.  No suite or other legal proceedings will be instituted elsewhere.

35.0    DETAILS OF ENCLOSURES:

The following are the attachments enclosed to this order, which form part of the contract.

1. 	Schedules  : Prices for Erection

2.	Annexure-B  : Prices Variation Clauses for Works

Please note that all other terms & conditions of Volume - I &II of specification (including Corrigendum) will form part of this Order.

Yours faithfully,

CHIEF ENGINEER/400kV

(For and on behalf of TSTRANSCO)

Copy shall be returned to TSTRANSCO by Contractor duly signed every page of this order in acknowledgement and acceptance of this order.

We accept the terms and conditions of this order.

SIGNATURE OF THE CONTRACTOR.

Copy to:

- DE (T) to Director (Projects & Grid Operation)/TSTRANSCO/Vidyut Soudha/ Hyd.

- Executive Director (Finance)/TSTRANSCO/Vidyut Soudha/Hyderabad.

- FA & CCA (Accounts) / TSTRANSCO/ Vidyut Soudha/Hyderabad.

- Chief Engineer/ 400kV/TSTRANSCO/Warangal.

- Chief Engineer/ Telecom /TSTRANSCO/Vidyut Soudha / Hyderabad.

- Chief Engineer/Civil/TSTRANSCO/Vidyut Soudha/ Hyderabad.

- Superintending Engineer/400kV/Construction/Karimnagar

- Superintending Engineer/Civil/TSTRANSCO/ Karimnagar.

- Executive Engineer / Civil/ Construction /Division/Karimnagar.

- Executive Engineer-2/400kV/ Construction/Karimanagr.

- SAO/P&A/TSTRANSCO/Vidyut Soudha/Hyderabad.

- SAO/B&BS/TSTRANSCO/Vidyut Soudha/Hyderabad.

- AO, O/o. Superintending Engineer/400kV/Construction/Karimnagar.

ANNEXURE-B

PRICE VARIATION (PV)  for Erection

i)	Price variation shall be applicable for both upward and downward variation in prices of respective items if the delivery of goods / work completion is within the stipulated period mentioned in the purchase order.

ii)	Wholesale Price Index, released from Ministry of Commerce & Industry, Govt. of India will be considered for the items cement, reinforcement steel.

iii)	The completion schedule enclosed to the specification in the form of bar chart shall be the basis for timing of the each activity for calculating the Price Variation during a month. If the schedule is not complied by the Contractor as per the above programme due to the reasons like right-of-way, the particular activity or task can be rescheduled by moving upward or downward on the time axis of the bar chart within the agreement period, as agreed by the Concerned Executive Engineer (Field Officer), as per the actual site conditions. In such cases, the concerned Executive Engineer will record the reasons for re-scheduling/delay of the work.

iv)	Price adjustment shall be calculated separately for reinforcement steel & cement components in proportion to the cost of work done involving the above materials during the billing period as given in the formula given below. The percentage of reinforcement steel & cement components is based on estimated rate only. The price variation amount so obtained will be added to the cost of work done calculated on quoted rate, put up for billing.

v)	The concerned Field Executive Engineer will calculate the Price Variation for the billing period, preferably monthly. For this purpose the contractor shall submit invoice supported by calculation as per formula specified along with documentary evidence for different indices applicable for Price Adjustment.

vi)	Price variation will be limited to the amount arrived based on schedule date of completion or actual date of completion which ever is earlier. Lower of the two indices values will be considered.

vii)	In specific cases like right-of-way problems, for which the contractor is not responsible, extension of the agreement period may be given duly rescheduling the programme of completion with the approval of competent authority. In all such cases, TSTRANSCO will consider application of Price variation clause case to case.

Applicable formula for calculating Price Variation for Re-inforcement steel, Cement:

The Price Variation applicable in respect of steel and cement utilized in civil works shall be as per G.O.Ms.No.94, Dt: 16-04-2008 and T.O.O CE (Civil) Ms.No.24,               Dt:23-04-2008  & T.O.O CE (Civil) Ms.No.84,  Dt: 12.06.2012 of TSTRANSCO subject to the following conditions:

a)	The price adjustment shall be applicable within original contract period or period extended on grounds of the departmental delays and valid reasons and shall not applicable to the extension granted on account of the Contractors fault.

b)	The price adjustment shall be applicable for actual components of items of works actually carried out during the period of bill and is allowed for steel and cement utilized in civil works, considering the absolute variation between the estimated rate and the rate approved by the Govt. based on the recommendation of Board of   Chief Engineers for the month. The base rate for Reinforcement Steel is Rs.35,000.00 per MT and for Cement Rs.4,750.00 per MT for the month of August' 2017.

c)	i) 	The price adjustment will be applied where the variation in rates only to the extent where it is above 5% over the estimated rates. Thus if the price excess is 10%, payment will be made only to the extent of 5% (10% - 5%). Further, the same procedure should be also followed for Negative Price variation.

ii) 	For the time extension period due to

a) 	department fault, price variation (Both +ve and –ve ) is applicable.

b) 	contractors fault, only negative price variation is applicable.

Necessary supplemental proposal regarding differential rate payable or difference rate recoverable on agreement rates of steel and cement utilized in civil works and structural steel due to price adjustment is to be submitted to the agreement concluding authority for approval.

d)	The Bidder shall indicate the total bid prices in Schedule-IIA attached to these documents.

e)	Deleted.

f)	The breakup of price in accordance with para above will be solely for the purpose of comparison of bids by the Purchaser and will not in any way limit the Purchaser's right to contract on any of the terms offered.

g)	The Bid price shall be written both in words and figures. In case of conflict between the figures and words, the latter shall prevail.  Corrections made by Bidder in figures, shall be specifically written in words for more clarity.

h)	Bid shall be submitted strictly as per the format outlined in the schedules, to enable Purchaser/Engineer to evaluate the bids expeditiously.

i)	The quantities stated in price schedule are approximate only and unit price shall apply to actual quantities measured on the completed work in accordance with specification and drawings.

CHIEF ENGINEER/400kV